## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM | SM/15636 | Support-WQMSP | Extension/Continuation work order for Engagement of Lab Personnel for the period from 01.04.2024 to 30.09.2024. | AE | JE1 | ORD/000691/2023-2024 | 138/BSSD | 28/03/2024 | 28/09/2024 | KHAYRASOLE PALLY MANGAL SAMITY | 2.55 | 0 | 0 | 30
2 | BIRBHUM |  | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM | SM/15636 | Support-WQMSP | Deployment/ Engagement for 5 Nos Sub- District Laboratory Personnel (5 nos. Chemist/Bacteriologist & 5 nos. Laboratory Assistant) & 1 no. Sampling Assistant (Ahmedpur Sub-Dist. Lab.) for a period of 06 months (01.07.2023 to 31.12.2023) for 5 nos. PHED Laboratories named Mayureswar Sub-District Laboratory, Patel Nagar Sub-District Laboratory, Ahmedpur Sub-District Laboratory , Murarai Sub-District Laboratory & Nalhati Sub district under Birbhum Didvision, P.H.E Dte | AE |  | ORD/000198/2023-2024 | 2220/BHM | 30/06/2023 | 31/12/2023 | DULAL MAJUMDAR | 12.14 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM | SM/15636 | Support-WQMSP | Operation and Mtc. of Water Testing Laboratory activities of the Birbhum District Laboratory at Suri under Birbhum Division, P.H.E. Dte. for the period of 06 (Six) months with effect from 01.07.2023 to 31.12.2023. | AE |  | ORD/000199/2023-2024 | 2219/BHM | 30/06/2023 | 31/12/2023 | DULAL MAJUMDAR | 6.49 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM | SM/15636 | Support-WQMSP | Engagement of Lab Personals for the Kanachi Khadi Bhandar (period from 01.04.2024 to 30.09.2024). | AE | JE3 | ORD/000756/2023-2024 | 197/RSD | 28/03/2024 | 27/09/2024 | KANACHI KHADI BHANDAR | 2.7 | 0 | 0 | 70
5 | BIRBHUM |  | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM | SM/15636 | Support-WQMSP | Engagement of Lab Personals for the Rampurhat Paribesh Pariseva (period from 01.04.2024 to 30.09.2024). | AE | JE3 | ORD/000760/2023-2024 | 198/RSD | 28/03/2024 | 27/09/2024 | RAMPURHAT PARIBESH PARISEVA | 2.7 | 0 | 0 | 70
6 | BIRBHUM |  | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM | SM/15636 | Support-WQMSP | Bill for Remuneration of Chemist, Bacteriologist, Lab-Assistant Under Rampurhat Paribesh pariseva Sub-District Laboratory (Name of NGO) for the period of April-2024 |  |  | BILL/00127/2024-2025 | BP-2024-25-56 | 17/05/2024 | 17/05/2024 | RAMPURHAT PARIBESH PARISEVA | 0.45 | 0 | 0 | 0
7 | BIRBHUM |  | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM | SM/15636 | Support-WQMSP | Bill for Remuneration of Chemist, Bacteriologist, Lab-Assistant Under Kanachi Khadi Bhandar Sub-District Laboratory (Name of NGO) for the period of MAY- 2024 |  |  | BILL/00260/2024-2025 | BP-2024-25-99 | 14/06/2024 | 14/06/2024 | KANACHI KHADI BHANDAR | 0.45 | 0 | 0 | 0
8 | BIRBHUM |  | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM | SM/15636 | Support-WQMSP | Bill for Remuneration of Chemist, Bacteriologist, Lab-Assistant Under Rampurhat Paribesh pariseva Sub-District Laboratory (Name of NGO) for the period of MAY-2024 |  |  | BILL/00262/2024-2025 | BP-2024-25-100 | 14/06/2024 | 14/06/2024 | RAMPURHAT PARIBESH PARISEVA | 0.45 | 0 | 0 | 0
9 | BIRBHUM |  | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM | SM/15636 | Support-WQMSP | Bill for Remuneration of Chemist, Bacteriologist, Lab-Assistant Under Kanachi Khadi Bhandar Sub-District Laboratory (Name of NGO) for the period of April - 2024. |  |  | BILL/00137/2024-2025 | BP-2024-25-57 | 17/05/2024 | 17/05/2024 | KANACHI KHADI BHANDAR | 0.45 | 0 | 0 | 0
10 | BIRBHUM |  | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM | SM/15636 | Support-WQMSP | Continuation Work OrderOperation and Mtc. of Water Testing Laboratory activities of the Birbhum District Laboratory at Suri under Birbhum Division, P.H.E. Dte. for the period of 01 (One) months with effect from 01.01.2024 to 31.01.2024. | AE | JE,JE2 | ORD/000701/2023-2024 | 4731/BHM | 29/12/2023 | 29/01/2024 | DULAL MAJUMDAR | 1.06 | 0 | 0 | 60
11 | BIRBHUM |  | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM | SM/15636 | Support-WQMSP | Extension/Continuation work order for Engagement of Lab Personnel for the period from 01.10.2024 to 31.03.2025. | AE | JE1 | ORD/000368/2024-2025 | 357/BSSD | 27/09/2024 | 28/03/2025 | KHAYRASOLE PALLY MANGAL SAMITY | 1.56 | 0 | 0 | 31
Total | [13 empty] | 31 | 0 | 0