## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Procurement of chemical & consumable for BirbhumDistrict Laboratory PHE Dte managed Laboratory (4 Nos) & NGo managed Laboratory(4 Nos) under Birbhum Division PHE Dte. For a period 03 months under Birbhum Division Phe Dte. | AE |  | ORD/001030/2021-2022 | 125/BHM | 24/01/2022 | 23/02/2022 | LAXMI ENTERPRISE | 15.7 | 15.7 | 100 | 0
2 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Procurement of chemical & consumable for Birbhum District Laboratory and 5 nos PHED managed Laboratory namely Mayureswar Sub-District Lab, Patel Nagar Sub Dist-District Lab, Ahmedpur Sub-District Lab, Nalhati Sub-District Lab and Murarai Sub- District Lab under Birbhum Division, PHE Dte. |  |  | ORD/000535/2022-2023 | 762/BHM | 09/03/2023 | 08/04/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 42.62 | 42.11 | 98.8 | 100
3 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Mayureswar Sub District Laboratory under Birbhum Division, PHE Dte. | AE | JE | ORD/000023/2025-2026 | 101/RWS | 06/05/2025 | 16/05/2025 | DULAL MAJUMDAR | 0.97 | 0 | 0 | 95
4 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Khayrasole Pally Mongal Samity Sub District Laboratory under Birbhum Division, PHE Dte. | AE | JE | ORD/000030/2025-2026 | 108/RWS | 06/05/2025 | 16/05/2025 | LAB ANALYTICS | 0.97 | 0 | 0 | 95
5 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Kanachi Khadi Bhandar Sub District Laboratory under Birbhum Division, PHE Dte. | AE | JE | ORD/000029/2025-2026 | 107/RWS | 06/05/2025 | 16/05/2025 | DULAL MAJUMDAR | 0.96 | 0 | 0 | 95
6 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Murarai Sub District Laboratory under Birbhum Division, PHE Dte. | AE | JE | ORD/000028/2025-2026 | 106/RWS | 06/05/2025 | 16/05/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.93 | 0 | 0 | 95
7 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Birbhum District Water Testing Laboratory under Birbhum Division, PHE Dte | AE | JE | ORD/000022/2025-2026 | 100/RWS | 06/05/2025 | 16/05/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.96 | 0 | 0 | 95
8 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Ahmedpur Sub District Laboratory under Birbhum Division, PHE Dte. | AE | JE | ORD/000026/2025-2026 | 104/RWS | 06/05/2025 | 16/05/2025 | LAB ANALYTICS | 0.98 | 0 | 0 | 95
9 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Patelnagar Sub District Laboratory under Birbhum Division, PHE Dte. | AE | JE | ORD/000027/2025-2026 | 105/RWS | 06/05/2025 | 16/05/2025 | LAB ANALYTICS | 0.98 | 0 | 0 | 95
10 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Nalhati Sub District Laboratory under Birbhum Division, PHE Dte. | AE | JE | ORD/000025/2025-2026 | 103/RWS | 06/05/2025 | 16/05/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.98 | 0 | 0 | 95
11 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Paribesh Pariseva Sub District Laboratory under Birbhum Division, PHE Dte. | AE | JE | ORD/000024/2025-2026 | 102/RWS | 06/05/2025 | 16/05/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.94 | 0 | 0 | 95
12 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Continuation Work Order for Engagement of Lab Personnels for the KANACHI KHADI BHANDAR( Period from 01.04.2026 TO 30.09.2026) | AE | Estimator,JE1 | ORD/000512/2025-2026 | 52/RWS | 13/03/2026 | 13/09/2026 | KANACHI KHADI BHANDAR | 2.7 | 0 | 0 | 45
13 | BIRBHUM |  | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. | SM/15637 | Support-WQMSP | Continuation Work order for Engagement of Lab personnels for the RAMPURHAT PARIBESH PARISEVA( Period from 01.04.2026 to 30.09.2026) | AE | Estimator,JE1 | ORD/000511/2025-2026 | 51/RWS | 13/03/2026 | 13/09/2026 | RAMPURHAT PARIBESH PARISEVA | 2.7 | 0 | 0 | 45
Total | [13 empty] | 72.4 | 57.81 | 79.85