## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Khoyrasol | Birbhum Division | Sagarbhanga Piped Water Supply Scheme (Khoyrasole Block) | SM/16270 | New | Preparation & Submission of DPR for Sagarbanga & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000680/2022-2023 | 131/BSSD | 14/07/2022 | 28/08/2022 | RADIANT | 1.23 | 1.23 | 100 | 100
2 | BIRBHUM | Khoyrasol | Birbhum Division | Sagarbhanga Piped Water Supply Scheme (Khoyrasole Block) | SM/16270 | New | Material Requisition To Resource Division |  |  | RTOR000250/2023-2024 | 422/BHM | 01/02/2024 | 01/02/2024 | Resource Division | 15.47 | 0 | 0 | 0
Total | [13 empty] | 16.7 | 1.23 | 7.39