## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Khoyrasol | Birbhum Division | Penchalia Piped Water Supply Scheme | SM/16282 | New | Preparation & Submission of DPR for Penchalia & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000679/2022-2023 | 126/BSSD | 12/07/2022 | 26/08/2022 | RADIANT | 2.43 | 0 | 0 | 100
2 | BIRBHUM | Khoyrasol | Birbhum Division | Penchalia Piped Water Supply Scheme | SM/16282 | New | Material Requisition To Resource Division |  |  | RTOR000248/2023-2024 | 429/BHM | 01/02/2024 | 01/02/2024 | Resource Division | 87.68 | 0 | 0 | 0
3 | BIRBHUM | Khoyrasol | Birbhum Division | Penchalia Piped Water Supply Scheme | SM/16282 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE,JE3 | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 31/01/2026 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
4 | BIRBHUM | Khoyrasol | Birbhum Division | Penchalia Piped Water Supply Scheme | SM/16282 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE,JE3 | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 31/12/2025 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
Total | [13 empty] | 5367.46 | 0 | 0