## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Birbhum Division | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/16373 | New | Continuation Work Order for Preparation & Submission of DPR for (Ramnagar) Water Supply Scheme under Mayureswar-II Development Block. | AE | JE3 | ORD/000622/2022-2023 | 203/RSD | 10/06/2022 | 25/07/2022 | ENVIROTECH SOLUTIONS | 4.29 | 0 | 0 | 100
2 | BIRBHUM | Mayureswar-II | Birbhum Division | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/16373 | New | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 1485/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 18.81 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/16373 | New | Providing Electro-mechanical accessories and others for Ramnagar PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000875/2023-2024 | 3513/Bol.MD | 24/11/2023 | 23/01/2024 | ORIENTAL ENGINEERING CO. | 55.45 | 0 | 0 | 65
4 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/16373 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Ramnagar PWSS under Mayureswar - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001241/2023-2024 | 532/BOL.MD | 14/03/2024 | 13/05/2024 | S.B.ENTERPRISE(BOLPUR) | 7.6 | 0 | 0 | 66
5 | BIRBHUM | Mayureswar-II | Birbhum Division | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/16373 | New | Material Requisition To Resource Division |  |  | RTOR000209/2023-2024 | 202/BHM | 22/01/2024 | 22/01/2024 | Resource Division | 5.83 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/16373 | New | WBSEDCL QUOTATION FOR RAMNAGAR P H NO I |  |  | BILL/01842/2023-2024 | BP-23-24-265 | 07/02/2024 | 07/02/2024 | WBSEDCL | 12.33 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/16373 | New | NEW POWER CONNECTION AT RAMNAGAR PWSS P/H No-II |  |  | BILL/00127/2024-2025 | BP-2024-2025-59 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.97 | 0 | 0 | 0
8 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/16373 | New | NEW SERVICE CONNECTION AT RAMNAGAR PWSS P/H No-III |  |  | BILL/00128/2024-2025 | BP-2024-2025-60 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.33 | 0 | 0 | 0
9 | BIRBHUM | Mayureswar-II | Birbhum Division | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. | SM/16373 | New | Different works related to Water Supply Scheme at RAMNAGAR & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000538/2022-2023 | 903/BHM | 22/03/2023 | 01/04/2025 | M/S.SUMAN CONSTRUCTION | 433.92 | 0 | 0 | 65
Total | [13 empty] | 557.53 | 0 | 0