## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rajnagar | Birbhum Division | Amlachaturi Piped Water Supply Scheme | SM/16387 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1574/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 20.07 | 0 | 0 | 0
2 | BIRBHUM | Rajnagar | Bolpur Mechanical | Amlachaturi Piped Water Supply Scheme | SM/16387 | New | QUOTATION FOR AMLACHATURI PWSS |  |  | BILL/00011/2024-2025 | BP-24-25-05 | 09/04/2024 | 09/04/2024 | WBSEDCL | 5.03 | 0 | 0 | 0
3 | BIRBHUM | Rajnagar | Bolpur Mechanical | Amlachaturi Piped Water Supply Scheme | SM/16387 | New | Providing Electro-mechanical accessories and others for Amlachaturi & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000525/2023-2024 | 2167/Bol.MD | 31/08/2023 | 06/04/2025 | SATYAJIT GHOSH | 88.42 | 0 | 0 | 85
4 | BIRBHUM | Rajnagar | Birbhum Division | Amlachaturi Piped Water Supply Scheme | SM/16387 | New | Different works related to water supply scheme at AMLACHATURI & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000401/2023-2024 | 4136/BHM | 18/10/2023 | 01/01/2026 | M/S KRIPASINDHU GHOSH & CO. | 531.73 | 0 | 0 | 20
Total | [13 empty] | 645.26 | 0 | 0