## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rajnagar | Birbhum Division | Amlachaturi Piped Water Supply Scheme | SM/16387 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1574/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 20.07 | 0 | 0 | 0
2 | BIRBHUM | Rajnagar | Bolpur Mechanical | Amlachaturi Piped Water Supply Scheme | SM/16387 | New | QUOTATION FOR AMLACHATURI PWSS |  |  | BILL/00011/2024-2025 | BP-24-25-05 | 09/04/2024 | 09/04/2024 | WBSEDCL | 5.03 | 0 | 0 | 0
3 | BIRBHUM | Rajnagar | Bolpur Mechanical | Amlachaturi Piped Water Supply Scheme | SM/16387 | New | Providing Electro-mechanical accessories and others for Amlachaturi & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000525/2023-2024 | 2167/Bol.MD | 31/08/2023 | 06/04/2025 | SATYAJIT GHOSH | 88.42 | 52.56 | 59.44 | 85
4 | BIRBHUM | Rajnagar | Birbhum Division | Amlachaturi Piped Water Supply Scheme | SM/16387 | New | Different works related to water supply scheme at AMLACHATURI & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000401/2023-2024 | 4136/BHM | 18/10/2023 | 01/10/2026 | M/S KRIPASINDHU GHOSH & CO. | 531.73 | 179.77 | 33.81 | 20
5 | BIRBHUM | Rajnagar | Birbhum Division | Amlachaturi Piped Water Supply Scheme | SM/16387 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
6 | BIRBHUM | Rajnagar | Bolpur Mechanical | Amlachaturi Piped Water Supply Scheme | SM/16387 | New | Supply & delivery of different electrical & mechanical accessories at Amlachaturi Piped water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000508/2024-2025 | 3755/Bol.MD | 12/09/2024 | 24/01/2025 | MENAKA ENTERPRISE | 21.86 | 5.79 | 26.48 | 100
Total | [13 empty] | 734.96 | 238.12 | 32.4