## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | New Pipe Testing Laboratory for testing of UPVC and HDPE pipes at Suri, Birbhum under Birbhum Division. | SM/16483 | Support-WQMSP | Supply, installation and commissioning of UPVC and HDPE pipes testing equipments including 1 year Operation & Maintenance of the same as per IS specification at Birbhum Divisional Office Complex at Suri , Birbhum. | AE(HQ) | Estimator | ORD/000200/2023-2024 | 3239/BHM | 25/07/2023 | 25/10/2023 | SUNIL RABI DAS | 94.98 | 89.67 | 94.41 | 100
Total | [13 empty] | 94.98 | 89.67 | 94.41