## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Birbhum Division | Chhora Piped Water Supply Scheme. | SM/16761 | New | Material Requisition To Resource Division |  |  | RTOR000146/2023-2024 | 1593/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 13.6 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-I | Birbhum Division | Chhora Piped Water Supply Scheme. | SM/16761 | New | Material Requisition To Resource Division |  |  | RTOR000028/2024-2025 | 2451/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 11.19 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Chhora Piped Water Supply Scheme. | SM/16761 | New | Providing Electro-mechanical accessories and others for Chhora & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000924/2023-2024 | 3530/Bol.MD | 29/11/2023 | 13/08/2025 | S.K.ELECTRICALS | 27.63 | 15.66 | 56.67 | 70
4 | BIRBHUM | Rampurhat-I | Birbhum Division | Chhora Piped Water Supply Scheme. | SM/16761 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 200 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at CHHORA & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE1,JE2 | ORD/000098/2024-2025 | 2116/BHM | 29/07/2024 | 29/07/2025 | ASIM KUMAR MONDAL | 400.06 | 0 | 0 | 30
Total | [13 empty] | 452.48 | 15.66 | 3.46