## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-II | Birbhum Division | Budhigram Piped Water Supply Scheme | SM/16762 | New | Continuation Work Order for Preparation & Submission of DPR for (Budhigram) Water Supply Scheme under Rampurhat-II Development Block. | AE | JE2 | ORD/000638/2022-2023 | 276/RSD | 18/08/2022 | 02/10/2022 | ECO CARE | 4.73 | 0 | 0 | 100
2 | BIRBHUM | Rampurhat-II | Birbhum Division | Budhigram Piped Water Supply Scheme | SM/16762 | New | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 1490/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 17.6 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Budhigram Piped Water Supply Scheme | SM/16762 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Budhigram PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001233/2023-2024 | 519/BOL.MD | 14/03/2024 | 26/02/2025 | TAPAN ENTERPRISE | 7.61 | 0 | 0 | 60
4 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Budhigram Piped Water Supply Scheme | SM/16762 | New | Providing Electro-mechanical accessories and others for Budhigram PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000474/2023-2024 | 2227/Bol.MD | 12/09/2023 | 31/07/2025 | SUNIL RABIDAS | 44.41 | 0 | 0 | 30
5 | BIRBHUM | Rampurhat-II | Birbhum Division | Budhigram Piped Water Supply Scheme | SM/16762 | New | Sinking of 250 X 150 mm Dia (through) and 180 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Budhigram & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2,JE3 | ORD/000413/2024-2025 | 3315/BHM | 04/12/2024 | 04/12/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 346.49 | 0 | 0 | 30
Total | [13 empty] | 420.84 | 0 | 0