## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Birbhum Division | Dhitora Right side and adjoining mouzas piped water supply scheme. | SM/17633 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 1501/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 10.63 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dhitora Right side and adjoining mouzas piped water supply scheme. | SM/17633 | New | QUOTATION BILL FOR DHITORA WS SCHEME P H NO.II |  |  | BILL/01356/2023-2024 | BP-23-24-148 | 28/11/2023 | 28/11/2023 | WBSEDCL | 2.61 | 0 | 0 | 0
3 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dhitora Right side and adjoining mouzas piped water supply scheme. | SM/17633 | New | QUOTATION BILL FOR DHITORA WS SCHEME P H NO.I |  |  | BILL/01355/2023-2024 | BP-23-24-147 | 28/11/2023 | 28/11/2023 | WBSEDCL | 3.81 | 0 | 0 | 0
4 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dhitora Right side and adjoining mouzas piped water supply scheme. | SM/17633 | New | Providing Electro-mechanical accessories and others for DHITORA RIGHT SIDE piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000390/2023-2024 | 1929/Bol.MD | 11/08/2023 | 01/07/2024 | ORIENTAL ENGINEERING CO. | 27.2 | 21.45 | 78.85 | 80
5 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dhitora Right side and adjoining mouzas piped water supply scheme. | SM/17633 | New | WBSEDCL QUOITATION FOR DHITORA PH NO-I |  |  | BILL/01838/2023-2024 | BP-23-24-268 | 08/02/2024 | 08/02/2024 | WBSEDCL | 1.3 | 0 | 0 | 0
6 | BIRBHUM | Murarai-I | Birbhum Division | Dhitora Right side and adjoining mouzas piped water supply scheme. | SM/17633 | New | Different works related to water supply scheme at DHITORA & its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000036/2023-2024 | 1108/BHM | 10/04/2023 | 01/03/2025 | M/S PROCHESTA ENTERPRISE | 215.75 | 155.26 | 71.96 | 100
Total | [13 empty] | 261.31 | 176.71 | 67.63