## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-II | Birbhum Division | Atkulia Piped Water Supply Scheme | SM/18301 | New | Preparation and submission of DPR for (Atkulia) Water Supply Scheme under Nalhati-II Development Block. | AE | JE2 | ORD/000755/2022-2023 | 218/AE/NSD | 18/04/2022 | 02/06/2022 | MS SOBHA AND CO | 4.89 | 4.89 | 100 | 100
2 | BIRBHUM | Nalhati-II | Birbhum Division | Atkulia Piped Water Supply Scheme | SM/18301 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 1510/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 62.89 | 0 | 0 | 0
3 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Atkulia Piped Water Supply Scheme | SM/18301 | New | Supply and Delivery of Open well Submersible Pumping Machineries and allied accessories for Atkulia PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000526/2024-2025 | 3784/BOL.MD | 12/09/2024 | 12/10/2024 | EASTERN INDIA SALES & SERVICE | 37.46 | 0 | 0 | 0
4 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Atkulia Piped Water Supply Scheme | SM/18301 | New | WBSEDCL QUOTATION FOR Atkulia Piped Water Supply Scheme |  |  | BILL/01604/2023-2024 | BP-23-24-237 | 29/01/2024 | 29/01/2024 | WBSEDCL | 3.29 | 0 | 0 | 0
5 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Atkulia Piped Water Supply Scheme | SM/18301 | New | Providing Electro-mechanical accessories and others for Atkulia PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000459/2023-2024 | 2134/Bol.MD | 25/08/2023 | 29/03/2025 | SINHA ELECTRICALS | 57.83 | 26.72 | 46.2 | 30
6 | BIRBHUM | Nalhati-II | Birbhum Division | Atkulia Piped Water Supply Scheme | SM/18301 | New | Jack pushing along with extension of pipeline (DI & HDPE), Restoration of Roads etc for Atkulia piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000670/2024-2025 | 799/BHM | 24/03/2025 | 19/03/2026 | M/S S. CHOUDHURY | 76.4 | 0 | 0 | 0
Total | [13 empty] | 242.74 | 31.6 | 13.02