## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Illambazar | Birbhum Division | Bhabani Water Supply Scheme | SM/18351 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHABANIPUR Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - B) | AE |  | ORD/000766/2022-2023 | 280/BSD | 22/07/2022 | 20/10/2022 | M/S R DUTTA & CO. | 4.29 | 0 | 0 | 100
2 | BIRBHUM | Illambazar | Birbhum Division | Bhabani Water Supply Scheme | SM/18351 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHABANIPUR Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - A) | AE |  | ORD/000765/2022-2023 | 176/BSD | 29/04/2022 | 28/07/2022 | M/S R DUTTA & CO. | 4.93 | 0 | 0 | 100
3 | BIRBHUM | Illambazar | Bolpur Mechanical | Bhabani Water Supply Scheme | SM/18351 | New | New service connection at Bhabanipur PWSS P.H.- I (Block- Illambazar) |  |  | BILL/00157/2024-2025 | BP-2024-2025-86 | 14/06/2024 | 14/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.93 | 0 | 0 | 0
4 | BIRBHUM | Illambazar | Central Drilling | Bhabani Water Supply Scheme | SM/18351 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | BIRBHUM | Illambazar | Birbhum Division | Bhabani Water Supply Scheme | SM/18351 | New | Different works related to water supply scheme at DHANASAHA, CHHATAR-BANDI, BHABANIPUR, BHUBANESWAR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | AE | JE1 | ORD/000384/2023-2024 | 4141/BHM | 19/10/2023 | 27/09/2025 | B RAI CONSTRUCTION COMPANY | 2996.46 | 0 | 0 | 5
Total | [13 empty] | 24350.38 | 0 | 0