## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | Daskalgram Piped Water Supply Scheme | SM/18353 | New | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 1488/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 74.7 | 0 | 0 | 0
2 | BIRBHUM | Nanoor | Birbhum Division | Daskalgram Piped Water Supply Scheme | SM/18353 | New | Work order for the work of construction of 300 Cum capacity O.H.R with soil investigation, 5.90 X 4.10 m pump room/ Chlorine room with sanitary arrangements. Laying of rising main, Distribution system with FHTC and different works related to DASKALGRAM PIPED WATER SUPPLY SCHEME (TSM/015491) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE2 ,JE2,Bolpur Sub-Division | ORD/000081/2024-2025 | 1784/BHM | 14/06/2024 | 14/06/2025 | NEW APOLLO HARDWARE | 663.67 | 0 | 0 | 0
3 | BIRBHUM | Nanoor | Birbhum Division | Daskalgram Piped Water Supply Scheme | SM/18353 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for DASKALGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - B) | AE | JE4 | ORD/000736/2022-2023 | 341/BSD | 05/09/2022 | 04/12/2022 | RADIANT | 2.54 | 1.85 | 72.85 | 100
4 | BIRBHUM | Nanoor | Birbhum Division | Daskalgram Piped Water Supply Scheme | SM/18353 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for DASKALGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | AE | JE4 | ORD/000778/2022-2023 | 255/BSD | 05/07/2022 | 03/10/2022 | RADIANT | 4.73 | 4.72 | 99.79 | 100
5 | BIRBHUM | Nanoor | Birbhum Division | Daskalgram Piped Water Supply Scheme | SM/18353 | New | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 2392/BHM | 27/08/2024 | 27/08/2024 | Resource Division | 15.79 | 0 | 0 | 0
6 | BIRBHUM | Nanoor | Central Drilling | Daskalgram Piped Water Supply Scheme | SM/18353 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 22101.2 | 6.57 | 0.03