## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | LAYEKPUR PIPED WATER SUPPLY SCHEME | SM/18361 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for LAYEKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE3 | ORD/000948/2022-2023 | 237/BSD | 17/06/2022 | 14/12/2022 | APEX ENGINEERING | 4.92 | 0 | 0 | 100
2 | BIRBHUM | Labpur | Birbhum Division | LAYEKPUR PIPED WATER SUPPLY SCHEME | SM/18361 | New | Continuation work for "Preparation & Submission of additional Detail Project Report (DPR) for LAYEKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE3 | ORD/000953/2022-2023 | 300/BSD | 10/08/2022 | 08/11/2022 | APEX ENGINEERING | 2.46 | 0 | 0 | 100
3 | BIRBHUM | Labpur | Birbhum Division | LAYEKPUR PIPED WATER SUPPLY SCHEME | SM/18361 | New | Construction of 400 Cum. OHR with Soil Investigation,Pump Room/Chlorine Room with sanitary arrangement,Laying of Rising Main Distribution System with FHTC and different works related to LAYEKPUR PIPED WATER SUPPLY SCHEME (TSM/016003) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE3 | ORD/000186/2024-2025 | 2771/BHM | 30/09/2024 | 30/09/2025 | SS ENTERPRISE | 663.03 | 0 | 0 | 0
4 | BIRBHUM | Labpur | Central Drilling | LAYEKPUR PIPED WATER SUPPLY SCHEME | SM/18361 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | BIRBHUM | Labpur | Bolpur Mechanical | LAYEKPUR PIPED WATER SUPPLY SCHEME | SM/18361 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Layekpur PWSS (TW No III), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001134/2024-2025 | 334/BOL.MD | 19/02/2025 | 19/06/2025 | M/S. UTTAM KUMAR CHATTERJEE | 37.24 | 0 | 0 | 0
6 | BIRBHUM | Labpur | Birbhum Division | LAYEKPUR PIPED WATER SUPPLY SCHEME | SM/18361 | New | Road restoration work for Layekpur Piped Water Supply Scheme, Labpur Block, under Birbhum Division, PHE Dte. | Assistant Engineer | JE3 | ORD/000250/2025-2026 | 2242/BHM | 29/08/2025 | 27/11/2025 | ARUP HAZRA | 27.91 | 0 | 0 | 0
Total | [13 empty] | 22075.33 | 0 | 0