## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Birbhum Division | Kusumba Piped Water Supply Scheme. | SM/18362 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 1466/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 13.68 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kusumba Piped Water Supply Scheme. | SM/18362 | New | Providing Electro-mechanical accessories and others for Kusumba Zone - I PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000912/2023-2024 | 3522/Bol.MD | 29/11/2023 | 28/01/2024 | PRADIP KUMAR DHABAL | 27.77 | 20.38 | 73.38 | 30
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Kusumba Piped Water Supply Scheme. | SM/18362 | New | Material Requisition To Resource Division |  |  | RTOR000035/2024-2025 | 2481/BHM | 03/09/2024 | 03/09/2024 | Resource Division | 24.98 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kusumba Piped Water Supply Scheme. | SM/18362 | New | Providing Electro-mechanical accessories and others for Kusumba Zone - II PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000410/2023-2024 | 2101/Bol.MD | 22/08/2023 | 11/04/2025 | MENAKA ENTERPRISE | 28.5 | 0 | 0 | 41
5 | BIRBHUM | Rampurhat-I | Birbhum Division | Kusumba Piped Water Supply Scheme. | SM/18362 | New | Construction of 200 CuM OHR (ZONE-I) & 350 CuM OHR (ZONE-II) with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, Rising main, Laying distribution( Z-I & II), Boundary wall,Land development,road restoration and Providing functional household tap connection and different works related to KUSUMBA & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1,JE2 | ORD/000122/2024-2025 | 2225/BHM | 12/08/2024 | 11/08/2026 | SUNIL RABI DAS | 800.42 | 0 | 0 | 20
Total | [13 empty] | 895.36 | 20.38 | 2.28