## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Dakhalbati Piped Water Supply Scheme. | SM/18363 | New | Supply and Installation of Low lift Pumping Machinery and other allied work for DHAKALBATI and Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000870/2023-2024 | 3377/Bol.MD | 13/10/2023 | 11/01/2024 | M. S. ENTERPRISE | 65.12 | 39.27 | 60.31 | 30
2 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Dakhalbati Piped Water Supply Scheme. | SM/18363 | New | Supply & Installation of High lift Pumping Mchinery and other allied work for DHAKALBATI & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000874/2023-2024 | 3367/BOL.MD | 11/10/2023 | 09/01/2024 | M. S. ENTERPRISE | 98.53 | 78.49 | 79.66 | 50
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Dakhalbati Piped Water Supply Scheme. | SM/18363 | New | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 2447/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 40.44 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-I | Birbhum Division | Dakhalbati Piped Water Supply Scheme. | SM/18363 | New | Sinking of 200 mm dia Alll through and 25 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM, 300 CuM, 250 CuM capacity O.H.R. for Zone-I, II and III respectively, 300 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I, II and III and Providing functional household tap connection related to water supply scheme at DAKHALBATI & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE1,JE2 | ORD/000110/2024-2025 | 2117/BHM | 29/07/2024 | 29/07/2025 | M/S GOUTAM DAS | 1419.03 | 25 | 1.76 | 15
5 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Dakhalbati Piped Water Supply Scheme. | SM/18363 | New | Quotation for new service connection at Dakhalbati PWSS Zone-III (Mouza- Binodpur) at Block- Rampurhat-I |  |  | BILL/00406/2025-2026 |  | 03/06/2025 | 03/06/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.56 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Dakhalbati Piped Water Supply Scheme. | SM/18363 | New | Quotation for new service connection at Dhakalbati High Lift (Block- Rampurhat-I) |  |  | BILL/00056/2025-2026 | 115/05 | 30/07/2025 | 30/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.2 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Dakhalbati Piped Water Supply Scheme. | SM/18363 | New | Quotation for new service connection at Dakhalbati OHR site Zone-II under Rampurhat-I block. |  |  | BILL/01973/2025-2026 |  | 06/01/2026 | 06/01/2026 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.01 | 0 | 0 | 0
Total | [13 empty] | 1647.88 | 142.76 | 8.66