## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Dakhalbati Piped Water Supply Scheme. | SM/18363 | New | Supply and Installation of Low lift Pumping Machinery and other allied work for DHAKALBATI and Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000870/2023-2024 | 3377/Bol.MD | 13/10/2023 | 11/01/2024 | M. S. ENTERPRISE | 65.12 | 0 | 0 | 30
2 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Dakhalbati Piped Water Supply Scheme. | SM/18363 | New | Supply & Installation of High lift Pumping Mchinery and other allied work for DHAKALBATI & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000874/2023-2024 | 3367/BOL.MD | 11/10/2023 | 09/01/2024 | M. S. ENTERPRISE | 98.53 | 0 | 0 | 50
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Dakhalbati Piped Water Supply Scheme. | SM/18363 | New | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 2447/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 40.44 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-I | Birbhum Division | Dakhalbati Piped Water Supply Scheme. | SM/18363 | New | Sinking of 200 mm dia Alll through and 25 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM, 300 CuM, 250 CuM capacity O.H.R. for Zone-I, II and III respectively, 300 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I, II and III and Providing functional household tap connection related to water supply scheme at DAKHALBATI & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE1,JE2 | ORD/000110/2024-2025 | 2117/BHM | 29/07/2024 | 29/07/2025 | M/S GOUTAM DAS | 1419.03 | 0 | 0 | 15
5 | BIRBHUM | Rampurhat-I | Birbhum Division | Dakhalbati Piped Water Supply Scheme. | SM/18363 | New | Continuation work for Supply of one no. Diesel Motor Cab/Maxi Cub (Air Condition) on hire basis under the Executive Engineer Birbhum Division P.H.E Dte (Period From 01.05.2025 to 31.07.2025) | AE(HQ) | Estimator | ORD/000224/2025-2026 | 1284/BHM | 30/04/2025 | 31/07/2025 | PREMANANDA ROY BISWAS | 0.47 | 0 | 0 | 100
Total | [13 empty] | 1623.59 | 0 | 0