## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Laying of Rising main with DI pipe line for MARGRAM water supply scheme under Rampurhat Sub-Division under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000642/2021-2022 | 99/RSD | 07/03/2022 | 06/04/2022 | TAPAS KUMAR SARKHEL | 2.41 | 0 | 0 | 100
2 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Wells and allieds works at Augmentation of Margram ( Pump House No - I, II & III ) Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000455/2023-2024 | 2132/Bol.MD | 25/08/2023 | 01/01/2027 | SUNIL RABIDAS | 90.64 | 55.06 | 60.75 | 80
3 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Providing and Installation of Starter Feeder Panel at existing Pump House Beside OHR and allied works at Margram ( Pump House No - IV ) Piped Water Supply Scheme, Block-Rampurhat-II [within Augmentation of Margram] under Bolpur Mechanical Division. PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000456/2023-2024 | 2133/Bol.MD | 25/08/2023 | 24/10/2023 | GOENKA ENTERPRISE | 6.55 | 6.54 | 99.9 | 100
4 | BIRBHUM |  | Birbhum Division | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Renovation of Existing Switch Room (Old head work site) size 5.40 mtr. X 3.65 mtr with Sanitary and water supply arrangement at Margram Piped Water Supply Scheme under Rampurhat Sub-Division, P.H.E. Dte. | AE | JE1 | ORD/000230/2023-2024 | 201/RSD | 28/07/2023 | 12/08/2023 | TAPAN ENTERPRISE | 0.97 | 0.95 | 97.89 | 100
5 | BIRBHUM |  | Birbhum Division | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Restoration works of concrete Road along with culverts (4nos) for Augmentation MARGRAM Water Supply Scheme under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000403/2023-2024 | 3516/BHM | 10/08/2023 | 09/10/2023 | PULAK KUMAR PAL | 16.34 | 16.28 | 99.59 | 100
6 | BIRBHUM |  | Birbhum Division | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Continuation Work Order For Supply and delivery of Sluice Valve for Augmentation of Margram W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. | AE(HQ) |  | ORD/000110/2023-2024 | 1632/BHM | 28/04/2023 | 28/05/2023 | MAKALI ENGINEERING CORPORATION | 9.57 | 9.57 | 100 | 100
7 | BIRBHUM |  | Birbhum Division | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, Boundary wall, Land development, Laying distribution, road restoration and Providing functional household tap connection related to AUGMENTATION OF MARGRAM & Its adjoining Mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE3 | ORD/000091/2024-2025 | 2006/BHM | 12/07/2024 | 09/01/2026 | PROJECT INDIA , 38/A, KHELAT BABU LANE, KOLKATA - 700037. | 692.88 | 46.75 | 6.75 | 35
8 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Supply & delivery of Sluice Valve & Non-Return Valve for Augmentation of Margram water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000440/2024-2025 | 1299./AE-III | 27/08/2024 | 03/09/2024 | SUNIL RABIDAS | 2.87 | 0 | 0 | 0
9 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Supply & delivery of Electrical accessories ie Main switch change over switch etc for Augmentation of Margram water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000547/2024-2025 | 1456./AE-III | 09/09/2024 | 16/09/2024 | BIRBHUM ELECTRIC WORKS | 2.88 | 0 | 0 | 100
10 | BIRBHUM |  | Birbhum Division | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Balance Laying of rising main along with road restoration other allied works for AUGMENTATION of MARGRAM & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000105/2025-2026 | 1750/BHM | 02/07/2025 | 30/09/2025 | PROJECT INDIA | 391.67 | 0 | 0 | 35
11 | BIRBHUM |  | Birbhum Division | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Hiring of Ambassador Car (Diesel/Petrol/Electric) registered Luxury Taxi for the office of the Assistant Engineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition with effect from 01.02.2025 to 31.01.2026 i.e. (365 Days) (For JJM Works) (SL. No. 01) | AE | JE3 | ORD/000565/2024-2025 | 133/RSD | 31/01/2025 | 31/01/2026 | PULAK KUMAR PAL | 1.72 | 0 | 0 | 0
12 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Quotation for new service connection at Augmentation of Margram PH-5 (Block - Rampurhat-II) |  |  | BILL/00007/2025-2026 | 115/03 | 30/07/2025 | 30/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.48 | 0 | 0 | 0
13 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Quotation for new service connection at Augmentation of Margram PH-6 (Block - Rampurhat-II) |  |  | BILL/00008/2025-2026 | 115/04 | 30/07/2025 | 30/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.19 | 0 | 0 | 0
14 | BIRBHUM |  | Birbhum Division | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2026-2027 | 1969/ BHM | 09/09/2026 | 09/09/2026 | Resource Division | 213.5 | 0 | 0 | 0
15 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Margram piped water supply scheme. | SM/18372 | Augmentation | Quotation for new service connection at Margram PWSS P/H- VII, block- Rampurhat-II, under Rampurhat CCC |  |  | BILL/01972/2025-2026 |  | 06/01/2026 | 06/01/2026 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 12.3 | 0 | 0 | 0
Total | [13 empty] | 1451.97 | 135.15 | 9.31