## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rajnagar | Birbhum Division | Gulalgachi Piped Supply Scheme | SM/18419 | New | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1453/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 435.57 | 0 | 0 | 0
2 | BIRBHUM | Rajnagar | Bolpur Mechanical | Gulalgachi Piped Supply Scheme | SM/18419 | New | QUOTATION FOR GULALGACHI PWSS RAJNAGAR BLOCK |  |  | BILL/00009/2024-2025 | BP-24-25-07 | 09/04/2024 | 09/04/2024 | WBSEDCL | 6.1 | 0 | 0 | 0
3 | BIRBHUM | Rajnagar | Bolpur Mechanical | Gulalgachi Piped Supply Scheme | SM/18419 | New | Providing electro-mechanical accessories and others for Gulalgachi water supply scheme in Rajnagar Block under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000386/2023-2024 | 1917/Bol.MD | 10/08/2023 | 04/09/2025 | DEY ENTERPRISE | 105.62 | 0 | 0 | 84
4 | BIRBHUM | Rajnagar | Bolpur Mechanical | Gulalgachi Piped Supply Scheme | SM/18419 | New | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/001232/2024-2025 | 1662/BOL.MD | 28/06/2024 | 14/01/2025 | SATYAJIT GHOSH | 0.57 | 1.49 | 259.43 | 100
5 | BIRBHUM | Rajnagar | Bolpur Mechanical | Gulalgachi Piped Supply Scheme | SM/18419 | New | Hiring of Luxury Car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/001077/2024-2025 | 4229/Bol.MD | 24/10/2024 | 22/02/2025 | RAJIB GHOSH | 0.57 | 1.61 | 279.93 | 100
6 | BIRBHUM | Rajnagar | Bolpur Mechanical | Gulalgachi Piped Supply Scheme | SM/18419 | New | Supply & delivery of different electrical accessories at Gulalgachi Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000518/2024-2025 | 3764/Bol.MD | 12/09/2024 | 09/05/2025 | STANDARD ELECTRICALS | 23.83 | 17.3 | 72.61 | 100
7 | BIRBHUM | Rajnagar | Birbhum Division | Gulalgachi Piped Supply Scheme | SM/18419 | New | Different works related to water supply scheme at GULALGACHI & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte | AE | JE1 | ORD/000389/2023-2024 | 4145/BHM | 19/10/2023 | 01/11/2025 | M/S SAHA AND MONDAL CONSTRUCTION | 635.78 | 297.91 | 46.86 | 10
Total | [13 empty] | 1208.05 | 318.32 | 26.35