## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Khoyrasol | Birbhum Division | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte | SM/18425 | New | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 3810/BHM | 12/09/2023 | 12/09/2023 | Resource Division | 1630.08 | 0 | 0 | 0
2 | BIRBHUM | Khoyrasol | Birbhum Division | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte | SM/18425 | New | Material Requisition To Resource Division |  |  | RTOR000262/2023-2024 | 623/BHM | 15/02/2024 | 15/02/2024 | Resource Division | 301.46 | 0 | 0 | 0
3 | BIRBHUM | Khoyrasol | Bolpur Mechanical | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte | SM/18425 | New | New service connection at Intake site for sub-surface based piped water supply scheme at Khoyrasole . |  |  | BILL/00084/2024-2025 | BP-2024-2025-21 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.9 | 0 | 0 | 0
4 | BIRBHUM | Khoyrasol | Birbhum Division | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte | SM/18425 | New | Survey, Planning, Design, Supply, Delivery, Erection, Construction, Commissioning and Completion in all respect all Civil and E&M Works including all allied, related and Enabling Works for 5.0 MGD capacity Radial Collector Well, Access Bridge, Substation Building, 1000 Cum capacity UGR with high lift Pump House and Raw Water Rising Main from Collector Well to River Bank UGR including 03(Three) months Trial Run and subsequent Operation & Maintenance for 1(One) year for Sub-Surface Water Based Piped Water Supply Scheme in Khairasole Block, District Birbhum on Turnkey basis under Birbhum Division, PHE Dte. | AE | JE | ORD/000580/2023-2024 | 445/BHM | 01/02/2024 | 01/08/2025 | G B CONSTRUCTION | 2150.9 | 0 | 0 | 70
5 | BIRBHUM | Khoyrasol | Bolpur Mechanical | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte | SM/18425 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at 20 nos. OHR site Piped water supply scheme of Khoyrasole project under Khoyrasole Block in the Dist. of Birbhum under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000579/2024-2025 | 3892/Bol.MD | 23/09/2024 | 23/09/2025 | SATYAJIT GHOSH | 145.74 | 0 | 0 | 68
Total | [13 empty] | 4239.08 | 0 | 0