## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Birbhum Division | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Different works related to water supply scheme at CHINPAI, LOBA & PARATPUR and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE1 | ORD/000265/2023-2024 | 3476/BHM | 08/08/2023 | 01/11/2026 | B RAI CONSTRUCTION COMPANY | 2497.19 | 267.6 | 10.72 | 45
2 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Providing electro-mechanical accessories and others for Chinpai & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000383/2023-2024 | 1914/Bol.MD | 10/08/2023 | 10/08/2024 | M/S P.P ELECTRICALS | 106.93 | 56.9 | 53.21 | 50
3 | BIRBHUM | Dubrajpur | Birbhum Division | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 1390/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 179.71 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Birbhum Division | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 3281/BHM | 27/07/2023 | 27/07/2023 | Resource Division | 1.02 | 0 | 0 | 0
5 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Supply and Delivery of Pump Starter, Diaphragm type Chlorinator dosing pump and Colum pipes at Chinpai and Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/001314/2023-2024 | 707/Bol.MD | 27/03/2024 | 26/04/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 7.99 | 7.99 | 100 | 100
6 | BIRBHUM | Dubrajpur | Birbhum Division | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Construction of 100 Cum Capacity CWR as per departmental drawing nearer to Kochujore for collection of water from Chinpai Head work site under Chinpai Piped Water Supply Scheme under Birbhum Sadar Sub- Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000056/2025-2026 | 308/BSSD | 22/05/2025 | 19/09/2025 | HIRANMAY GHOSH | 17.82 | 0 | 0 | 100
7 | BIRBHUM | Dubrajpur | Birbhum Division | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Laying of rising main pipe line, Jack Pushing of Railway & NH-14 for Chinpai Piped Water Supply Scheme in Rajnagar Block under Birbhum Sadar Sub-Division, PHE Dte. within Birbhum Division, P.H.E. Dte. | AE | JE2 | ORD/000219/2025-2026 | 2164/BHM | 20/08/2025 | 18/11/2025 | B RAI CONSTRUCTION COMPANY | 73.46 | 0 | 0 | 0
8 | BIRBHUM | Dubrajpur | Birbhum Division | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Construction of 100 Cum Capacity CWR as per departmental drawing nearer to Purba Bonkati for collection of water from Chinpai Head work site under Chinpai Piped Water Supply Scheme under Birbhum Sadar Sub- Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000055/2025-2026 | 307/BSSD | 22/05/2025 | 21/06/2025 | MUKHERJEE ENTERPRISE | 17.82 | 0 | 0 | 100
9 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Chinpai Piped Water Supply Scheme. | SM/18462 | New | New Power connection at Chinpai PWSS (L/L) |  |  | BILL/01692/2024-2025 | 98/11 | 17/07/2025 | 17/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.5 | 0 | 0 | 0
10 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Quotation for new service connection at Chinpai PWSS H/L site under Dubrajpur Block |  |  | BILL/01694/2024-2025 | 98/12 | 17/07/2025 | 17/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.96 | 0 | 0 | 0
Total | [13 empty] | 2927.4 | 332.48 | 11.36