## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Masra Piped Water Supply Scheme. | SM/18463 | New | Providing Electro-mechanical accessories and others for Masra Zone - II PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000877/2023-2024 | 3520/BOL.MD | 29/11/2023 | 28/01/2024 | CINZANO | 28.82 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Masra Piped Water Supply Scheme. | SM/18463 | New | Providing Electro-mechanical accessories and others for Masra Zone - I PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000910/2023-2024 | 3521/Bol.MD | 29/11/2023 | 28/01/2024 | DEY ENTERPRISE | 27.71 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Masra Piped Water Supply Scheme. | SM/18463 | New | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 1571/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 14.85 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-I | Birbhum Division | Masra Piped Water Supply Scheme. | SM/18463 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuMOHR (ZONE-I) & 350 CuM (ZONE-II) ,Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at MASHRA & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE,JE3 | ORD/000145/2024-2025 | 2514/BHM | 04/09/2024 | 04/09/2025 | GARGO TRADERS | 915.63 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-I | Birbhum Division | Masra Piped Water Supply Scheme. | SM/18463 | New | Material Requisition To Resource Division |  |  | RTOR000044/2024-2025 | 3264/BHM | 02/12/2024 | 02/12/2024 | Resource Division | 24.27 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Masra Piped Water Supply Scheme. | SM/18463 | New | Quotation for new service connection at Masra PWSS PH-I, z-1, Mouza-Nirisha, Block- Rampurhat-I under Mollarpur CCC |  |  | BILL/00348/2025-2026 |  | 06/05/2025 | 06/05/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.59 | 0 | 0 | 0
Total | [13 empty] | 1015.87 | 0 | 0