## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | KANAIPUR PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/18489 | New | Providing Submersible pumping machineries and other electromechanical equipments and installation at KANAIPUR PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | Assistant Engineer-III | Junior Engineer | ORD/001219/2023-2024 | 404/Bol.MD | 07/03/2024 | 21/04/2024 | M. S. ENTERPRISE | 29 | 21.49 | 74.1 | 70
2 | BIRBHUM | Mayureswar-I | Bolpur Mechanical | KANAIPUR PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/18489 | New | Providing Electro-mechanical accessories and others for Kanaipur PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000729/2023-2024 | 3475/Bol.MD | 07/11/2023 | 30/06/2025 | SINHA ELECTRICALS | 57.22 | 29.83 | 52.12 | 80
3 | BIRBHUM | Mayureswar-I | Birbhum Division | KANAIPUR PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/18489 | New | Different works related to water supply scheme at BIRCHANDRAPUR, ASURLAYA, BARATURIGRAM & KANAIPUR and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | AE | JE2,JE3 | ORD/000471/2023-2024 | 505/BHM | 05/02/2024 | 30/09/2025 | B RAI CONSTRUCTION COMPANY | 2071.77 | 67.19 | 3.24 | 20
Total | [13 empty] | 2158 | 118.5 | 5.49