## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | MANIKPUR PIPED WATER SUPPLY SCHEME | SM/18509 | New | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 1626/BHM | 28/04/2023 | 28/04/2023 | Resource Division | 103.84 | 0 | 0 | 0
2 | BIRBHUM | Labpur | Birbhum Division | MANIKPUR PIPED WATER SUPPLY SCHEME | SM/18509 | New | Continuation work for "Preparation & Submission of additional Detail Project Report (DPR) for MANIKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.¿. | AE | JE3 | ORD/000954/2022-2023 | 301/BSD | 10/08/2022 | 06/02/2023 | APEX ENGINEERING | 2.11 | 0 | 0 | 100
3 | BIRBHUM | Labpur | Birbhum Division | MANIKPUR PIPED WATER SUPPLY SCHEME | SM/18509 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for MANIKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE3 | ORD/000949/2022-2023 | 244/BSD | 24/06/2022 | 22/09/2022 | APEX ENGINEERING | 4.92 | 0 | 0 | 100
4 | BIRBHUM | Labpur | Birbhum Division | MANIKPUR PIPED WATER SUPPLY SCHEME | SM/18509 | New | Different works related to water supply scheme at MANIKPUR PIPED WATER SUPPLY SCHEME (TSM/016147) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte.(2nd Call) | AE | JE3 | ORD/000388/2023-2024 | 4144/BHM | 19/10/2023 | 30/09/2025 | M/S SAHA AND MONDAL CONSTRUCTION | 785.13 | 0 | 0 | 15
5 | BIRBHUM | Labpur | Bolpur Mechanical | MANIKPUR PIPED WATER SUPPLY SCHEME | SM/18509 | New | New service connection at Manikpur PH-I W/S scheme Block - Labpur under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/00360/2025-2026 | 98/14 | 17/07/2025 | 17/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.1 | 0 | 0 | 0
6 | BIRBHUM | Labpur | Central Drilling | MANIKPUR PIPED WATER SUPPLY SCHEME | SM/18509 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 66.26 | 0.31 | 11
Total | [13 empty] | 22241.87 | 66.26 | 0.3