## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Providing Electro-mechanical accessories and others for Mahesha PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000840/2023-2024 | 3279/Bol.MD | 29/09/2023 | 28/11/2023 | WEST BENGAL ENGINEERING CO. | 66.12 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-II | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1446/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 50.7 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Supply, delivery and storage of different Electro-Mechanical accessories at Mahesha PWSS under Bolpur Mmechanical Dsivision, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000512/2024-2025 | 3759/Bol.MD | 12/09/2024 | 12/10/2024 | P. K. ENGINEERING | 16.05 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Mahesha Piped Water Supply Scheme, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/000516/2024-2025 | 3762/Bol.MD | 12/09/2024 | 12/10/2024 | QUAZI NOZRUL ISLAM | 25.33 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar-II | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Continuation Work Order for Preparation & Submission of DPR for (MAHESHA) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000840/2022-2023 | 324/RSD | 08/09/2022 | 23/10/2022 | ENVIROTECH SOLUTIONS | 3.54 | 2.55 | 71.94 | 100
6 | BIRBHUM | Mayureswar-II | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Continuation Work Order for Preparation & Submission of DPR for (MAHESHA) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE | JE3 | ORD/000841/2022-2023 | 435/RSD | 21/11/2022 | 05/01/2023 | ENVIROTECH SOLUTIONS | 3.54 | 3.53 | 99.64 | 100
7 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Supply, delivery and Installation of Centrifugal pumping machinery at Mahesha PWSS under Bolpur Mechanical Division, P.H.E. Dte. of Mayureswar - II Block | Assistant Engineer-III | Junior Engineer | ORD/001191/2023-2024 | 376/Bol.MD | 06/03/2024 | 20/04/2024 | MITRA ENTERPRISE | 7.69 | 7.69 | 100 | 100
8 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Replacement of PDB cum MCC Panel including other allieds works at Mahesha PWSS under Bolpur Mechanical Division, P.H.E. Dte. Of Mayureswar - II block. | Assistant Engineer-III | Junior Engineer | ORD/001194/2023-2024 | 378/Bol.MD | 06/03/2024 | 20/04/2024 | J.K.ENGINEERING CO | 7.25 | 7.08 | 97.65 | 100
9 | BIRBHUM | Mayureswar-II | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Material Requisition To Resource Division |  |  | RTOR000015/2024-2025 | 2390/BHM | 27/08/2024 | 27/08/2024 | Resource Division | 16.84 | 0 | 0 | 0
10 | BIRBHUM | Mayureswar-II | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Sinking of 250 X 150 mm Dia, 150 m deep Tube Well Drilling by Direct Rotary method, Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing FHTC, related to water supply scheme at Mahesha & its adjoining mouzas water supply scheme within Mayureswar-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE2 | ORD/000086/2024-2025 | 1952/BHM | 04/07/2024 | 01/11/2026 | S K CONSTRUCTION VILL& POST - DEBKUNDA, P.S - BELDANGA, DIST - MURSHIDABAD | 609.18 | 42.96 | 7.05 | 60
11 | BIRBHUM | Mayureswar-II | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
12 | BIRBHUM | Mayureswar-II | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Erection of Sign Board (900mm X 600mm) for demarcation of land at various places under Birbhum Division, PHE Dte. | AE,AE(HQ) | Estimator,JE | ORD/000458/2024-2025 | 3608/BHM | 31/12/2024 | 31/03/2025 | IMAGIN | 40.29 | 0 | 0 | 95
13 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | New Service Connection at Mahesha PWSS P/H-II |  |  | BILL/01801/2024-2025 | 98/4 | 17/07/2025 | 17/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.11 | 0 | 0 | 0
14 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | New Service Connection at Mahesha PWSS P/H-IV |  |  | BILL/01800/2024-2025 | 98/05 | 17/07/2025 | 17/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.85 | 0 | 0 | 0
Total | [13 empty] | 923.33 | 63.8 | 6.91