## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Providing Electro-mechanical accessories and others for Mahesha PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000840/2023-2024 | 3279/Bol.MD | 29/09/2023 | 28/11/2023 | WEST BENGAL ENGINEERING CO. | 66.12 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-II | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1446/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 50.7 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Supply, delivery and storage of different Electro-Mechanical accessories at Mahesha PWSS under Bolpur Mmechanical Dsivision, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000512/2024-2025 | 3759/Bol.MD | 12/09/2024 | 12/10/2024 | P. K. ENGINEERING | 16.05 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Mahesha Piped Water Supply Scheme, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/000516/2024-2025 | 3762/Bol.MD | 12/09/2024 | 12/10/2024 | QUAZI NOZRUL ISLAM | 25.33 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar-II | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Continuation Work Order for Preparation & Submission of DPR for (MAHESHA) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000840/2022-2023 | 324/RSD | 08/09/2022 | 23/10/2022 | ENVIROTECH SOLUTIONS | 3.54 | 2.55 | 71.94 | 100
6 | BIRBHUM | Mayureswar-II | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Continuation Work Order for Preparation & Submission of DPR for (MAHESHA) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE | JE3 | ORD/000841/2022-2023 | 435/RSD | 21/11/2022 | 05/01/2023 | ENVIROTECH SOLUTIONS | 3.54 | 3.53 | 99.64 | 100
7 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Supply, delivery and Installation of Centrifugal pumping machinery at Mahesha PWSS under Bolpur Mechanical Division, P.H.E. Dte. of Mayureswar - II Block | Assistant Engineer-III | Junior Engineer | ORD/001191/2023-2024 | 376/Bol.MD | 06/03/2024 | 20/04/2024 | MITRA ENTERPRISE | 7.69 | 7.69 | 100 | 100
8 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Replacement of PDB cum MCC Panel including other allieds works at Mahesha PWSS under Bolpur Mechanical Division, P.H.E. Dte. Of Mayureswar - II block. | Assistant Engineer-III | Junior Engineer | ORD/001194/2023-2024 | 378/Bol.MD | 06/03/2024 | 20/04/2024 | J.K.ENGINEERING CO | 7.25 | 7.08 | 97.65 | 100
9 | BIRBHUM | Mayureswar-II | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Material Requisition To Resource Division |  |  | RTOR000015/2024-2025 | 2390/BHM | 27/08/2024 | 27/08/2024 | Resource Division | 16.84 | 0 | 0 | 0
10 | BIRBHUM | Mayureswar-II | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district | SM/18510 | New | Sinking of 250 X 150 mm Dia, 150 m deep Tube Well Drilling by Direct Rotary method, Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing FHTC, related to water supply scheme at Mahesha & its adjoining mouzas water supply scheme within Mayureswar-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE2 | ORD/000086/2024-2025 | 1952/BHM | 04/07/2024 | 01/11/2026 | S K CONSTRUCTION VILL& POST - DEBKUNDA, P.S - BELDANGA, DIST - MURSHIDABAD | 609.18 | 42.96 | 7.05 | 60
Total | [13 empty] | 806.23 | 63.8 | 7.91