## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Loba Piped Water Supply Scheme. | SM/18511 | New | Providing electro-mechanical accessories and others for Loba & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000384/2023-2024 | 1915/Bol.MD | 10/08/2023 | 10/08/2024 | SINHA ELECTRICALS | 129.72 | 81.76 | 63.03 | 70
2 | BIRBHUM | Dubrajpur | Birbhum Division | Loba Piped Water Supply Scheme. | SM/18511 | New | Material Requisition To Resource Division |  |  | RTOR000072/2022-2023 | 1396/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 454.99 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Loba Piped Water Supply Scheme. | SM/18511 | New | Supply & delivery of openwell submersible pumping machinery for Loba Piped water supply scheme under Bolpur Mechanical Division, PHE Dte |  |  | ORD/000835/2024-2025 | 1676./AE-III | 24/10/2024 | 31/10/2024 | MASSK ENGINEERING WORKS | 2.75 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Loba Piped Water Supply Scheme. | SM/18511 | New | Supply & delivery of different electrical accessories at Loba Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000465/2024-2025 | 1310./AE-III | 28/08/2024 | 01/01/2025 | RMD TRADING | 2.78 | 2.78 | 100 | 100
5 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Loba Piped Water Supply Scheme. | SM/18511 | New | Supply & delivery of different electrical accessories at Loba Piped water supply scheme under Bolpur Mechanical Division P,H,E,Dte. | Assistant Engineer-III | Junior Engineer | ORD/000633/2024-2025 | 1203./AE-III | 16/08/2024 | 26/08/2024 | J.K.ENGINEERING CO | 0.97 | 0.97 | 100 | 100
6 | BIRBHUM | Dubrajpur | Birbhum Division | Loba Piped Water Supply Scheme. | SM/18511 | New | Different works related to water supply scheme at CHINPAI, LOBA & PARATPUR and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE1 | ORD/000265/2023-2024 | 3476/BHM | 08/08/2023 | 01/11/2025 | B RAI CONSTRUCTION COMPANY | 2497.19 | 230.59 | 9.23 | 45
7 | BIRBHUM | Dubrajpur | Birbhum Division | Loba Piped Water Supply Scheme. | SM/18511 | New | Road crossing, Repairing & restoration of damaged pipe lines & PCC roads, sluice valve chambers, Construction of 300 Cum OHR, Pump House, Laying Distribution System, Rising Main Connection including all allied works for Loba Piped Water Supply Scheme under Birbhum division, PHE Dte". | AE | JE1 | ORD/000255/2025-2026 | 2828/BHM | 11/11/2025 | 11/11/2026 | S S ENTERPRISE | 260.79 | 0 | 0 | 0
8 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Loba Piped Water Supply Scheme. | SM/18511 | New | Supply and Delivery of Pump Starter, Chlorinator dosing pump at Loba & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000984/2024-2025 | 2028./AE-III | 19/12/2024 | 03/01/2025 | AHALYA ENGINEERING WORKS | 3.98 | 1.06 | 26.48 | 100
Total | [13 empty] | 3353.19 | 317.16 | 9.46