## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Charicha Piped Water Supply Scheme. | SM/18512 | New | Supply & Installation of Low lift Pumping Mchinery and other allied work for CHARICHA & Adjoining moujas water supply scheme within Md. Bazar Block under Bolpur Mechanical Division PHE | Driller in Charge | Junior Engineer | ORD/000550/2023-2024 | 2146/Bol.MD | 25/08/2023 | 23/11/2023 | KAMAKHYA ENTERPRISE | 31.63 | 0 | 0 | 0
2 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Charicha Piped Water Supply Scheme. | SM/18512 | New | Supply & Installation of High lift Pumping Mchinery and other allied work for CHARICHA & Adjoining moujas water supply scheme within Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000551/2023-2024 | 2147/Bol.MD | 25/08/2023 | 23/11/2023 | DEY ENTERPRISE | 90.92 | 0 | 0 | 0
3 | BIRBHUM | Mohammad Bazar | Birbhum Division | Charicha Piped Water Supply Scheme. | SM/18512 | New | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 1622/BHM | 28/04/2023 | 28/04/2023 | Resource Division | 248.27 | 0 | 0 | 0
4 | BIRBHUM | Mohammad Bazar | Birbhum Division | Charicha Piped Water Supply Scheme. | SM/18512 | New | Different works related to water supply scheme at CHARICHA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (2nd Call) | AE(HQ) | JE1 | ORD/000396/2023-2024 | 4164/BHM | 30/10/2023 | 30/06/2025 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 970.91 | 0 | 0 | 35
Total | [13 empty] | 1341.72 | 0 | 0