## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 1448/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 72.7 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-II | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Continuation Work Order for Preparation & Submission of DPR for (CHHOTA TURIGRAM) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE | JE3 | ORD/000837/2022-2023 | 380/RSD | 26/09/2022 | 10/11/2022 | ENVIROTECH SOLUTIONS | 3.29 | 0 | 0 | 100
3 | BIRBHUM | Mayureswar-II | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Continuation Work Order for Preparation & Submission of DPR for (CHHOTA TURIGRAM ) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000836/2022-2023 | 292/RSD | 02/09/2022 | 17/10/2022 | ENVIROTECH SOLUTIONS | 3.36 | 0 | 0 | 100
4 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Well and other allied works at Chototurigram PWSS under Bolpur Mechanical Division., Block - Mayureswar - II. | Assistant Engineer-III | Junior Engineer | ORD/001193/2023-2024 | 377/Bol.MD | 06/03/2024 | 20/04/2024 | CINZANO | 7.75 | 0 | 0 | 100
5 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Well and other allied works at Chototurigram PWSS under Bolpur Mechanical Division., Block - Mayureswar - II. | Assistant Engineer-III | Junior Engineer | ORD/001190/2023-2024 | 375/Bol.MD | 06/03/2024 | 20/04/2024 | STANDARD ELECTRICALS | 7.41 | 0 | 0 | 100
6 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Supply, Delivery and storage of different Electro-Mechanical Accessories at Chhoto Tuligram PWSS under Bolpur Mechanical Division, PHE,Dte. | Assistant Engineer-III | Junior Engineer | ORD/000513/2024-2025 | 3760/Bol.MD | 12/09/2024 | 01/01/2025 | HINDOL ROY | 40.82 | 0 | 0 | 100
7 | BIRBHUM | Mayureswar-II | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 2382/BHM | 27/08/2024 | 27/08/2024 | Resource Division | 14.74 | 0 | 0 | 0
8 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Providing Electro-mechanical accessories and others for Chhoto Turigram PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000843/2023-2024 | 3282/BOL.MD | 29/09/2023 | 31/10/2025 | SINHA ELECTRICALS | 67.61 | 0 | 0 | 40
9 | BIRBHUM | Mayureswar-II | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
Total | [13 empty] | 285.52 | 0 | 0