## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | SM/18514 | New | Providing Electro-mechanical accessories and others for Bara Kartik Chungri PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000990/2023-2024 | 3597/Bol.MD | 08/12/2023 | 06/02/2024 | A. G. ENTERPRISE | 55.74 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-II | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | SM/18514 | New | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 1515/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 112.15 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-II | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | SM/18514 | New | Different works related to water supply scheme at Madhupur, Khamedda & Bara-Karttikchungri and its adjoining mouzas water supply scheme within Rampurhat-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | AE | JE3 | ORD/000395/2023-2024 | 4163/BHM | 30/10/2023 | 12/05/2025 | M/S ASHA CONSTRUCTION | 1089.94 | 65.16 | 5.98 | 40
4 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | SM/18514 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Wells and allieds works at Bara Kartik Chungri Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division. | Assistant Engineer-III | Junior Engineer | ORD/000523/2024-2025 | 3782/BOL.MD | 12/09/2024 | 12/10/2024 | ORIENTAL ENGINEERING CO. | 24.94 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-II | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | SM/18514 | New | Continuation Work Order for Preparation & Submission of DPR for (BARA KARTIK CHUNGRI) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | AE | JE3 | ORD/000788/2022-2023 | 297/RSD | 07/09/2022 | 22/10/2022 | ECO CARE | 3.13 | 3.04 | 97.14 | 100
6 | BIRBHUM | Rampurhat-II | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | SM/18514 | New | Continuation Work Order for Preparation & Submission of DPR for (BARA KARTIK CHUNGRI) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | AE | JE3 | ORD/000800/2022-2023 | 417/RSD | 18/10/2022 | 02/12/2022 | ECO CARE | 2.91 | 2.55 | 87.59 | 100
7 | BIRBHUM | Rampurhat-II | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | SM/18514 | New | Continuation Work Order for Preparation & Submission of DPR for (BARA KARTIK CHUNGRI) Water Supply Scheme (Part-C) under Rampurhat-II Development Block. | AE | JE3 | ORD/000801/2022-2023 | 439/RSD | 29/11/2022 | 13/01/2023 | ECO CARE | 1.82 | 1.54 | 84.63 | 100
8 | BIRBHUM | Rampurhat-II | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | SM/18514 | New | Material Requisition To Resource Division |  |  | RTOR000229/2023-2024 | 226/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 3.7 | 0 | 0 | 0
9 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | SM/18514 | New | WBSEDCL QUOTATION MONEY FOR BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME |  |  | BILL/01589/2023-2024 | BP-23-24-223 | 15/01/2024 | 15/01/2024 | WBSEDCL | 16.88 | 0 | 0 | 0
Total | [13 empty] | 1311.18 | 72.29 | 5.51