## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Kankalitala piped water supply scheme. | SM/18518 | New | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 1546/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 214.47 | 0 | 0 | 0
2 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Kankalitala piped water supply scheme. | SM/18518 | New | Supply and delivery of chlorinator dosing pump for kankalitala Water Supply Project under Bolpur Mechanical Divn. P.H.E. Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000551/2024-2025 | 3819/BOL.MD | 18/09/2024 | 08/10/2024 | SINHA ELECTRICALS | 3.24 | 0 | 0 | 100
3 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Kankalitala piped water supply scheme. | SM/18518 | New | WBSEDCL QUOTATION FOR KANKALITALA PWSS |  |  | BILL/01590/2023-2024 | BP-23-24-222 | 15/01/2024 | 15/01/2024 | WBSEDCL | 10.64 | 0 | 0 | 0
4 | BIRBHUM | Bolpur Sriniketan | Central Drilling | Kankalitala piped water supply scheme. | SM/18518 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Kankalitala piped water supply scheme. | SM/18518 | New | Providing Electro-mechanical accessories and others for Kankalitala & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000484/2023-2024 | 2240/BOL.MD. | 13/09/2023 | 01/07/2025 | SINHA ELECTRICALS | 74.39 | 0 | 0 | 80
6 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Kankalitala piped water supply scheme. | SM/18518 | New | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE4 | ORD/000402/2023-2024 | 4139/BHM | 18/10/2023 | 31/12/2025 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 0 | 0 | 60
Total | [13 empty] | 24327.49 | 0 | 0