## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Mostala Piped Water Supply Scheme. | SM/18519 | New | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 1362/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 133.81 | 0 | 0 | 0
2 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Mostala Piped Water Supply Scheme. | SM/18519 | New | Providing Electro-mechanical accessories and others for Mostala & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000486/2023-2024 | 2241/BOL.MD. | 13/09/2023 | 01/01/2025 | SINHA ELECTRICALS | 85.42 | 0 | 0 | 78
3 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Mostala Piped Water Supply Scheme. | SM/18519 | New | Different works related to water supply scheme at MONOHARPUR, MOSTALA, RUPPUR & SALAN Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE4,JE_BLK_NANOOR | ORD/000398/2023-2024 | 4137/BHM | 18/10/2023 | 09/01/2026 | NAUTANDAS AND CO | 2897.79 | 0 | 0 | 10
4 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Mostala Piped Water Supply Scheme. | SM/18519 | New | Supply and delivery of Submersible pump for ikshudhara Water Supply Scheme(T/W - I) under Bolpur Mechanical Divn. PHE Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000604/2024-2025 | 3850/BOL.MD | 18/09/2024 | 08/10/2024 | SWAPAN BANERJEE | 2.62 | 0 | 0 | 100
5 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Mostala Piped Water Supply Scheme. | SM/18519 | New | Supply and delivery of Submersible pump for ikshudhara Water Supply Scheme (T/W-II) under Bolpur Mechanical Divn. PHE Dte. |  | Junior Engineer | ORD/000655/2024-2025 | 3873/BOL.MD | 19/09/2024 | 09/10/2024 | M/S. S.S. ENTERPRISE | 2.75 | 0 | 0 | 0
6 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Mostala Piped Water Supply Scheme. | SM/18519 | New | Supply and delivery of M.S. seamless column pipe for Mostala water supply Scheme under BOL MD, PHE Dte.. | Assistant Engineer (HQ) | Junior Engineer | ORD/000814/2024-2025 | 4194/BOL.MD | 22/10/2024 | 11/11/2024 | EASTERN INDIA SALES & SERVICE | 2.94 | 0 | 0 | 100
7 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Mostala Piped Water Supply Scheme. | SM/18519 | New | Supply & delivery of submersible cable accessories at mostala water supply scheme T.W No-II under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000558/2024-2025 | 3822/BOL.MD | 18/09/2024 | 08/10/2024 | STANDARD ELECTRICALS | 2.8 | 0 | 0 | 100
8 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Mostala Piped Water Supply Scheme. | SM/18519 | New | Supply & delivery of submersible cable accessories at Mostala water supply scheme T.W No-I under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000553/2024-2025 | 3820/BOL.MD | 18/09/2024 | 08/10/2024 | RAJIB GHOSH | 3.07 | 0 | 0 | 100
9 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Mostala Piped Water Supply Scheme. | SM/18519 | New | WBSEDCL QUOTATION FOR MOSTALA WS SCHEME |  |  | BILL/01593/2023-2024 | BP-23-24-219 | 15/01/2024 | 15/01/2024 | WBSEDCL | 5.37 | 0 | 0 | 0
10 | BIRBHUM | Bolpur Sriniketan | Central Drilling | Mostala Piped Water Supply Scheme. | SM/18519 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 24476.33 | 0 | 0