## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Birbhum Division | Sahapur Piped Water Supply Scheme. | SM/18520 | New | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 1512/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 154.79 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. | SM/18520 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Sahapur PWSS under Dubrajpur Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001245/2023-2024 | 533/BOL.MD | 14/03/2024 | 13/05/2024 | M/S.S.S. ENTERPRISE | 7.62 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. | SM/18520 | New | Providing Electro-mechanical accessories and others for Sahapur and Adjoining moujas water supply scheme under Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001264/2023-2024 | 562/BOL.MD | 15/03/2024 | 14/04/2024 | BENGAL CONSTRUCTION | 3.84 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Birbhum Division | Sahapur Piped Water Supply Scheme. | SM/18520 | New | Continuation Work Order for Preparation & Submission of DPR for (SAHAPUR) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | AE | JE3 | ORD/000796/2022-2023 | 358/RSD | 15/09/2022 | 30/10/2022 | ECO CARE | 2.91 | 2.9 | 99.68 | 100
5 | BIRBHUM | Dubrajpur | Birbhum Division | Sahapur Piped Water Supply Scheme. | SM/18520 | New | Continuation Work Order for Preparation & Submission of DPR for (SAHAPUR) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | AE | JE3 | ORD/000785/2022-2023 | 285/RSD | 26/08/2022 | 10/10/2022 | ECO CARE | 3.63 | 3.01 | 82.84 | 100
6 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. | SM/18520 | New | Installation of Submersible pumping Machineries at newly sunk Tube Wells and allied works at Sahapur PWSS, Block- Dubrajpur under Bolpur Mechanical Division. | Assistant Engineer-III | Junior Engineer | ORD/000541/2024-2025 | 3800/BOL.MD | 12/09/2024 | 12/10/2024 | SWAPAN ENTERPRISE | 6.82 | 6.81 | 99.91 | 100
7 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. | SM/18520 | New | Supply, Delivery & Installation of Submersible Pumpining Machinery at newly sunk River Bed Tube well no - 1, 2 ,3 and other allied works at Sahapur Piped water supply scheme (Block- Rampurhat II) | Assistant Engineer-III | Junior Engineer | ORD/001209/2023-2024 | 371/BOL.MD | 06/03/2024 | 05/04/2024 | CINZANO | 16.91 | 15.63 | 92.45 | 100
8 | BIRBHUM | Dubrajpur | Birbhum Division | Sahapur Piped Water Supply Scheme. | SM/18520 | New | Material Requisition To Resource Division |  |  | RTOR000021/2024-2025 | 2444/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 29.08 | 0 | 0 | 0
9 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. | SM/18520 | New | Quotation for new service connection at Sahapur TW No-II (Block-Rampurhat-II) |  |  | BILL/02221/2023-2024 | BP-2023-24-305 | 18/03/2024 | 18/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.21 | 0 | 0 | 0
10 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. | SM/18520 | New | WBSEDCL QUOTATION FOR SAHAPUR TW-1 |  |  | BILL/02247/2023-2024 | BP-2023-24-306 | 18/03/2024 | 18/03/2024 | WBSEDCL | 4.89 | 0 | 0 | 0
11 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. | SM/18520 | New | Providing Electro-mechanical accessories and others for Sahapur PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000485/2023-2024 | 2235/Bol.MD | 12/09/2023 | 01/05/2025 | QUAZI NOZRUL ISLAM | 44.39 | 19.51 | 43.96 | 50
12 | BIRBHUM | Dubrajpur | Birbhum Division | Sahapur Piped Water Supply Scheme. | SM/18520 | New | Sinking of 250 mm. X 200 mm Dia deep tubewell ,250 CuM capacity CWR, Pump room/ Chlorine room with/without sanitary arrangements( different size),and laying of Rising main,Distribution System (Zone -I & II ) with FHTC and different works related to SAHAPUR & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE,JE1,JE3 | ORD/000094/2024-2025 | 2126/BHM | 30/07/2024 | 30/07/2025 | KINGS & CO. | 685.99 | 0 | 0 | 20
13 | BIRBHUM | Dubrajpur | Birbhum Division | Sahapur Piped Water Supply Scheme. | SM/18520 | New | Soil Investigation & Construction of Over Head Reservoir of capacity 350 Cum (Zone-I) & 300 Cum (Zone-II) related to water supply scheme at SAHAPUR & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000204/2025-2026 | 2160/BHM | 20/08/2025 | 20/08/2026 | ARPAN PANDIT | 215.34 | 0 | 0 | 0
Total | [13 empty] | 1179.43 | 47.87 | 4.06