## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-II | Birbhum Division | Beloa Piped Water Supply Scheme | SM/18522 | New | Preparation and submission of DPR for (Beloa) Water Supply Scheme under Nalhati-II Development Block. | AE | JE2 | ORD/000756/2022-2023 | 219/AE/NSD | 18/04/2022 | 02/06/2022 | MS SOBHA AND CO | 4.92 | 0 | 0 | 100
2 | BIRBHUM | Nalhati-II | Birbhum Division | Beloa Piped Water Supply Scheme | SM/18522 | New | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 1511/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 55.88 | 0 | 0 | 0
3 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Beloa Piped Water Supply Scheme | SM/18522 | New | Supply and Delivery of Valves, Cetrifugal Pumping Machineries and allied accessories for Beloa PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000522/2024-2025 | 3781/BOL.MD | 12/09/2024 | 12/10/2024 | SATYAJIT GHOSH | 32.39 | 0 | 0 | 0
4 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Beloa Piped Water Supply Scheme | SM/18522 | New | Quotation for new service connection at Beloa TW No-III (Block-Nalhati-II) |  |  | BILL/00034/2024-2025 | BP-24-25-12 | 25/04/2024 | 25/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.38 | 0 | 0 | 0
5 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Beloa Piped Water Supply Scheme | SM/18522 | New | WBSEDCL QUOTATION FOR BELOA P H .II WS SCHEME |  |  | BILL/01602/2023-2024 | BP-23-24-161 | 15/01/2024 | 15/01/2024 | WBSEDCL | 3.73 | 0 | 0 | 0
6 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Beloa Piped Water Supply Scheme | SM/18522 | New | WBSEDCL QUOTATION FOR BELOA WS SCHEME |  |  | BILL/01603/2023-2024 | BP-23-24-231 | 15/01/2024 | 15/01/2024 | WBSEDCL | 4.7 | 0 | 0 | 0
7 | BIRBHUM | Nalhati-II | Birbhum Division | Beloa Piped Water Supply Scheme | SM/18522 | New | Different works for works related to water supply scheme at HAZARIPUR, Beloa & its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000255/2023-2024 | 3425/BHM | 02/08/2023 | 01/01/2026 | M/S NATIONAL CONSTRUCTION | 1099.34 | 0 | 0 | 15
8 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Beloa Piped Water Supply Scheme | SM/18522 | New | Providing Electro-mechanical accessories and others for Beloa PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000461/2023-2024 | 2135/Bol.MD | 25/08/2023 | 01/03/2025 | QUAZI NOZRUL ISLAM | 56.05 | 0 | 0 | 40
9 | BIRBHUM | Nalhati-II | Birbhum Division | Beloa Piped Water Supply Scheme | SM/18522 | New | Restoration of Roads, pucca drain including Jack pushing & Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Beloa piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000199/2025-2026 | 2135/BHM | 18/08/2025 | 14/02/2026 | M/S S. CHOUDHURY | 53.37 | 0 | 0 | 70
Total | [13 empty] | 1314.76 | 0 | 0