## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Birbhum Division | Ayas Piped Water Supply Scheme. | SM/18669 | New | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 1495/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 249.36 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Ayas Piped Water Supply Scheme. | SM/18669 | New | Supply and Installation of High lift Pumping Machinery and other allied work for AYAS and Adjoining moujas water supply scheme under within Rampurhat - I Block Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000872/2023-2024 | 3372/Bol.MD | 12/10/2023 | 01/07/2025 | SINHA ELECTRICALS | 95.35 | 70.38 | 73.81 | 30
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Ayas Piped Water Supply Scheme. | SM/18669 | New | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 2389/BHM | 27/08/2024 | 27/08/2024 | Resource Division | 42.26 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Ayas Piped Water Supply Scheme. | SM/18669 | New | Supply & Installation of Low lift Pumping Mchinery and other allied work for AYAS & Adjoining moujas water supply scheme under within Rampurhat - I Block Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000869/2023-2024 | 3389/BOL.MD | 16/10/2023 | 01/04/2025 | S.K.ELECTRICALS | 59.94 | 28.63 | 47.76 | 50
5 | BIRBHUM | Rampurhat-I | Birbhum Division | Ayas Piped Water Supply Scheme. | SM/18669 | New | Sinking of 250 X 150 mm Dia (through) and 25 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM, 300 CuM, 150 CuM capacity O.H.R. for Zone-I, II and III respectively, 300 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I, II and III and Providing functional household tap connection related to water supply scheme at AYAS & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE1,JE3 | ORD/000088/2024-2025 | 1949/BHM | 04/07/2024 | 31/03/2026 | PRADIP KUMAR DEB, 103/4 NAINAN PARA LANE , KOLKATA-700036 | 1332.94 | 0 | 0 | 55
Total | [13 empty] | 1779.86 | 99.01 | 5.56