## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kashtagara Piped Water Supply Scheme. | SM/18733 | New | Providing Electro-mechanical accessories and others for Kashtagara Zone - II PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000914/2023-2024 | 3523/Bol.MD | 29/11/2023 | 28/01/2024 | M/S. DILIP MITRA | 27.61 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kashtagara Piped Water Supply Scheme. | SM/18733 | New | Providing Electro-mechanical accessories and others for Kashtagara Zone - I PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000916/2023-2024 | 3524/Bol.MD | 29/11/2023 | 28/01/2024 | WEST BENGAL ENGINEERING CO. | 27.68 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Kashtagara Piped Water Supply Scheme. | SM/18733 | New | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 1589/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 13.11 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-I | Birbhum Division | Kashtagara Piped Water Supply Scheme. | SM/18733 | New | Sinking of 200 mm dia all through and 150 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements,, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I and II and Providing functional household tap connection related to water supply scheme at Kashtagara and Adjoining Moujas Piped Water Supply Scheme within RAMPURHAT-I Block underBIRBHUM Division, PHE Dte. | AE | JE,JE2 | ORD/000365/2024-2025 | 3141/BHM | 19/11/2024 | 19/11/2025 | M/S DIPAK ENTERPRISE | 895.59 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kashtagara Piped Water Supply Scheme. | SM/18733 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Kastagara PWSS under Rampurhat - I Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001247/2023-2024 | 524/BOL.MD | 14/03/2024 | 13/05/2024 | S.G.TECHNICAL SERVICES | 7.61 | 6.21 | 81.54 | 40
6 | BIRBHUM | Rampurhat-I | Birbhum Division | Kashtagara Piped Water Supply Scheme. | SM/18733 | New | Material Requisition To Resource Division |  |  | RTOR000046/2024-2025 | 3263/BHM | 02/12/2024 | 02/12/2024 | Resource Division | 26.95 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kashtagara Piped Water Supply Scheme. | SM/18733 | New | Quotation for new service connection at Kastogara PWSS PH-II, Z-II, Mouza- Saonsa, Block- Rampurhat-I under Mollarpur CCC |  |  | BILL/00346/2025-2026 |  | 06/05/2025 | 06/05/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.74 | 0 | 0 | 0
8 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kashtagara Piped Water Supply Scheme. | SM/18733 | New | Quotation for new service connection at Kastogara PWSS PH-I , Z-II, site- kastagara , block- Rampurhat-I under Mollarpur ccc |  |  | BILL/00347/2025-2026 |  | 06/05/2025 | 06/05/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.15 | 0 | 0 | 0
Total | [13 empty] | 1006.44 | 6.21 | 0.62