## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Rasa Phase-II water supply scheme, Block-Khoyrasole, District- Birbhum | SM/18783 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasa in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.(Sl. No.9) | AE | JE1 | ORD/000410/2022-2023 | 2587/BHM | 22/11/2022 | 21/01/2023 | HIRANMAY GHOSH | 58.98 | 0 | 0 | 49
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Rasa Phase-II water supply scheme, Block-Khoyrasole, District- Birbhum | SM/18783 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area of Rasa W/S Scheme in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte. | AE | JE,JE2, Birbhum Sadar Sub-Division | ORD/000338/2023-2024 | 3895/BHM | 21/09/2023 | 20/11/2023 | HIRANMAY GHOSH | 74.96 | 13.11 | 17.49 | 72
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Rasa Phase-II water supply scheme, Block-Khoyrasole, District- Birbhum | SM/18783 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area of Rasa W/S Scheme in Suri Sadar Sub-Division under Birbhum Division, PHE Dte. | AE | JE2, Birbhum Sadar Sub-Division | ORD/000369/2023-2024 | 3750/BHM | 05/09/2023 | 20/10/2023 | RICK CONSTRUCTION | 9.92 | 0 | 0 | 100
Total | [13 empty] | 143.86 | 13.11 | 9.12