## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. | SM/18787 | Augmentation | Providing and installation of Low Lift Pumping Machineries including other works for Augmentation of Dubrajpur (Rural) Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. Block : Dubrajpur, Dist : Birbhum | Assistant Engineer-III | Junior Engineer | ORD/001046/2023-2024 | 06/BOL.MD | 03/01/2024 | 02/04/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 41.18 | 28.93 | 70.26 | 40
2 | BIRBHUM |  | Birbhum Division | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. | SM/18787 | Augmentation | Sinking of Tubewell, Construction of OHR, Construction of Boundary wall, pump house and laying distribution system along with FHTC works at Augmentation of Dubrajpur (Rural) & its adjoining mouzas water supply scheme within Dubrajpur under Birbhum Division, PHE Dte. (2nd Call) | AE | JE3 | ORD/000472/2023-2024 | 524/BHM | 05/02/2024 | 01/09/2025 | KOUSIK DAS | 457.67 | 72.69 | 15.88 | 64
3 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. | SM/18787 | Augmentation | Providing and installation of High Lift Pumping Machineries including others at Augmentation of Dubrajpur (Rural) Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. Block : Dubrajpur, Dist : Birbhum. | Assistant Engineer-III | Junior Engineer | ORD/001045/2023-2024 | 05/BOL.MD | 03/01/2024 | 02/04/2024 | SATYAJIT GHOSH | 78.65 | 34.24 | 43.53 | 40
4 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. | SM/18787 | Augmentation | Replacement of PDB cum MCC Panel including other allieds works at Augmentation of Dubrajpur Water Supply Scheme under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/001212/2023-2024 | 374/BOL.MD | 06/03/2024 | 05/04/2024 | BIRBHUM ELECTRIC WORKS | 8.61 | 8.61 | 100 | 100
5 | BIRBHUM |  | Birbhum Division | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. | SM/18787 | Augmentation | Allied work for Construction of Boundary wall near Mama Bhagne Pahar & Shifting of Rising main pipe line near Sal River Bridge due to pipe line beneath the NH Road under the Augmentation of Dubrajpur Rural Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. Within Birbhum Division, P.H.E. Dte | AE | JE2, Birbhum Sadar Sub-Division,JE3 | ORD/000514/2023-2024 | 662/BHM | 20/02/2024 | 05/04/2024 | RICK CONSTRUCTION | 4.04 | 3.9 | 96.45 | 100
6 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. | SM/18787 | Augmentation | Repairing of Gasious Chlorination system and others at Dubrajpur Aug. water supply scheme under Bolpur Mechanical Division PHE, Dte | Assistant Engineer-III | Junior Engineer | ORD/001313/2023-2024 | 604./AE-III | 27/03/2024 | 17/04/2024 | ORIENTAL ENGINEERING CO. | 3.84 | 3.83 | 99.78 | 100
7 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. | SM/18787 | Augmentation | Supply & Delivery at site of 10 H.P Submersible Pumping Machinery for Beluti PWSS at Mayureswar-II Block under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001343/2023-2024 | 612./AE-III | 27/03/2024 | 03/04/2024 | DEY ENTERPRISE | 1.82 | 0 | 0 | 100
8 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. | SM/18787 | Augmentation | Supply, delivery and storage of different Electro-Mechanical accessories at Augmentation of Dubrajpur PWSS under Bolpur Mmechanical Dsivision, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000511/2024-2025 | 3758/Bol.MD | 12/09/2024 | 01/03/2025 | M. S. ENTERPRISE | 39.41 | 25.39 | 64.42 | 100
Total | [13 empty] | 635.24 | 177.6 | 27.96