## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & surveillance under JJM under Birbhum Division PHE Dte. | SM/19263 | Support-WQMSP | Deployment/ Engagement for 5 Nos Sub- District Laboratory Personnel (5 nos. Chemist/Bacteriologist & 5 nos. Laboratory Assistant) & 1 no. Sampling Assistant (Ahmedpur Sub-Dist. Lab.) for a period of 01(One) years with effect from 01.01.2024 to 31.12.2024 for 5 nos. PHED Laboratories named Mayureswar Sub-District Laboratory, Patel Nagar Sub-District Laboratory, Ahmedpur Sub-District Laboratory, Murarai Sub-District Laboratory & Nalhati Sub district under Birbhum Division, P.H.E Dte. | AE | JE,JE3 | ORD/000517/2023-2024 | 383/BHM | 29/12/2023 | 29/12/2024 | DULAL MAJUMDAR | 35.34 | 13.29 | 37.61 | 92
2 | BIRBHUM |  | Birbhum Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & surveillance under JJM under Birbhum Division PHE Dte. | SM/19263 | Support-WQMSP | Deployment/ Engagement for 5 Nos. Sub- District Laboratory Personnel (10 nos. Chemist/Bacteriologist & 5 nos. Laboratory Assistant) & 4 no. Sampling Assistant for a period of 01(One) years for 5 nos. PHED Laboratories named Mayureswar Sub-District Laboratory, Patel Nagar Sub-District Laboratory, Ahmedpur Sub-District Laboratory, Murarai Sub-District Laboratory & Nalhati Sub-district under Birbhum Division, P.H.E Dte.(With effect from 01.02.2025 to 31.01.2026) | AE | Estimator,JE | ORD/000583/2024-2025 | 295/BHM | 27/01/2025 | 27/01/2026 | CFS MANAGEMENT PRIVATE LIMITED | 40.19 | 12.98 | 32.29 | 86
3 | BIRBHUM |  | Birbhum Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & surveillance under JJM under Birbhum Division PHE Dte. | SM/19263 | Support-WQMSP | Continuation work order for Engagement of Lab personals for the Rampurhat Paribesh Pariseva( Period from 01.10.2025 to 31.03.2026) | AE | Estimator,JE | ORD/000285/2025-2026 | 170/RWS | 23/09/2025 | 23/03/2026 | RAMPURHAT PARIBESH PARISEVA | 2.7 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & surveillance under JJM under Birbhum Division PHE Dte. | SM/19263 | Support-WQMSP | Continuation Work Order for Operation and Mtc. of Water Testing Laboratory activities of the Birbhum District Laboratory at Suri under Birbhum Division, P.H.E. Dte. for the period of 02(Two) Months with effect from 01.02.2025 to 31.03.2025. | AE | Estimator,JE | ORD/000620/2024-2025 | 373/BHM | 31/01/2025 | 31/03/2025 | SAKTI ENTERPRISE | 2.08 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & surveillance under JJM under Birbhum Division PHE Dte. | SM/19263 | Support-WQMSP | Operation and Mtc. of Water Testing Laboratory activities of the Birbhum District Laboratory at Suri under Birbhum Division, P.H.E. Dte. for the period of 01(One) years.(With Effects From 01.04.2025 to 31.03.2026) | AE,AE(HQ) | Estimator,JE1 | ORD/000654/2024-2025 | 759/BHM | 20/03/2025 | 20/03/2026 | SAKTI ENTERPRISE | 14.66 | 0 | 0 | 100
Total | [13 empty] | 94.97 | 26.27 | 27.66