## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Bolpur Mechanical | Solarisation for NET metering of different PWSS at different Blocks under Bolpur Mechanical Division,PHED | SM/16381 | IOT | Solarization for NET metering of 18 Nos. PWSS at different blocks under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000048/2023-2024 | 1134/Bol.MD | 14/06/2023 | 11/12/2023 | PERFECT RENEWABLE AGENCY | 107.85 | 53.92 | 50 | 100
Total | [13 empty] | 107.85 | 53.92 | 50