## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Paschim Bardhaman | Assistant Engineer | Junior Engineer | ORD/000191/2023-2024 | 3372/RS | 08/11/2023 | 08/05/2024 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 92.57 | 85.51 | 92.37 | 50
2 | NADIA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Paschim Bardhaman | Assistant Engineer | Junior Engineer | ORD/000191/2023-2024 | 3372/RS | 08/11/2023 | 08/05/2024 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 92.57 | 85.51 | 92.37 | 50
3 | PASCHIM BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Paschim Bardhaman | Assistant Engineer | Junior Engineer | ORD/000191/2023-2024 | 3372/RS | 08/11/2023 | 08/05/2024 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 92.57 | 85.51 | 92.37 | 50
4 | SOUTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Paschim Bardhaman | Assistant Engineer | Junior Engineer | ORD/000191/2023-2024 | 3372/RS | 08/11/2023 | 08/05/2024 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 92.57 | 85.51 | 92.37 | 50
5 | BIRBHUM |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Nadia District. | Assistant Engineer | Junior Engineer | ORD/000093/2023-2024 | 2681/RS | 29/08/2023 | 27/02/2024 | IMAGIN | 217.78 | 217.78 | 100 | 99
6 | NADIA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Nadia District. | Assistant Engineer | Junior Engineer | ORD/000093/2023-2024 | 2681/RS | 29/08/2023 | 27/02/2024 | IMAGIN | 217.78 | 217.78 | 100 | 99
7 | PASCHIM BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Nadia District. | Assistant Engineer | Junior Engineer | ORD/000093/2023-2024 | 2681/RS | 29/08/2023 | 27/02/2024 | IMAGIN | 217.78 | 217.78 | 100 | 99
8 | SOUTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Nadia District. | Assistant Engineer | Junior Engineer | ORD/000093/2023-2024 | 2681/RS | 29/08/2023 | 27/02/2024 | IMAGIN | 217.78 | 217.78 | 100 | 99
9 | BIRBHUM |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the South24 Parganas | Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 2708/RS | 31/08/2023 | 29/02/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 230.91 | 230.91 | 100 | 99
10 | NADIA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the South24 Parganas | Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 2708/RS | 31/08/2023 | 29/02/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 230.91 | 230.91 | 100 | 99
11 | PASCHIM BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the South24 Parganas | Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 2708/RS | 31/08/2023 | 29/02/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 230.91 | 230.91 | 100 | 99
12 | SOUTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the South24 Parganas | Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 2708/RS | 31/08/2023 | 29/02/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 230.91 | 230.91 | 100 | 99
13 | BIRBHUM |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Birbhum District. | Assistant Engineer | Junior Engineer | ORD/000094/2023-2024 | 2682/RS | 29/08/2023 | 27/02/2024 | IMAGIN | 213.42 | 213.42 | 100 | 99
14 | NADIA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Birbhum District. | Assistant Engineer | Junior Engineer | ORD/000094/2023-2024 | 2682/RS | 29/08/2023 | 27/02/2024 | IMAGIN | 213.42 | 213.42 | 100 | 99
15 | PASCHIM BARDHAMAN |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Birbhum District. | Assistant Engineer | Junior Engineer | ORD/000094/2023-2024 | 2682/RS | 29/08/2023 | 27/02/2024 | IMAGIN | 213.42 | 213.42 | 100 | 99
16 | SOUTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas, Nadia, Birbhum and Paschim Bardhaman districts Under Jal Jeevan Mission (JJM) Support Activities | SM/18999 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Birbhum District. | Assistant Engineer | Junior Engineer | ORD/000094/2023-2024 | 2682/RS | 29/08/2023 | 27/02/2024 | IMAGIN | 213.42 | 213.42 | 100 | 99
Total | [13 empty] | 3018.74 | 2990.5 | 99.06