## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Nadia and Birbhum districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19233 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Birbhum District. | Assistant Engineer | Junior Engineer | ORD/000313/2023-2024 | 711/RS | 01/03/2024 | 01/01/2025 | IMAGIN | 332.28 | 281.59 | 84.75 | 50
2 | NADIA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Nadia and Birbhum districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19233 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Birbhum District. | Assistant Engineer | Junior Engineer | ORD/000313/2023-2024 | 711/RS | 01/03/2024 | 01/01/2025 | IMAGIN | 332.28 | 281.59 | 84.75 | 50
3 | BIRBHUM |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Nadia and Birbhum districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19233 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Nadia District. | Assistant Engineer | Junior Engineer | ORD/000322/2023-2024 | 713/RS | 01/03/2024 | 01/01/2025 | IMAGIN | 336 | 284.75 | 84.75 | 50
4 | NADIA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Nadia and Birbhum districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19233 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Nadia District. | Assistant Engineer | Junior Engineer | ORD/000322/2023-2024 | 713/RS | 01/03/2024 | 01/01/2025 | IMAGIN | 336 | 284.75 | 84.75 | 50
5 | BIRBHUM |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Nadia and Birbhum districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19233 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Nadia District. | Assistant Engineer | Junior Engineer | ORD/000204/2024-2025 | 3171/RS | 30/12/2024 | 30/03/2025 | IMAGIN | 109.75 | 0 | 0 | 99
6 | NADIA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Nadia and Birbhum districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19233 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Nadia District. | Assistant Engineer | Junior Engineer | ORD/000204/2024-2025 | 3171/RS | 30/12/2024 | 30/03/2025 | IMAGIN | 109.75 | 0 | 0 | 99
Total | [13 empty] | 1556.05 | 1132.67 | 72.79