## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Nadia and Birbhum districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19356 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Birbhum District. | Assistant Engineer | Junior Engineer | ORD/000202/2024-2025 | 3169/RS | 30/12/2024 | 30/03/2025 | IMAGIN | 105.33 | 0 | 0 | 99
2 | NADIA |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Nadia and Birbhum districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19356 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Birbhum District. | Assistant Engineer | Junior Engineer | ORD/000202/2024-2025 | 3169/RS | 30/12/2024 | 30/03/2025 | IMAGIN | 105.33 | 0 | 0 | 99
3 | BIRBHUM |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Nadia and Birbhum districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19356 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Nadia District. | Assistant Engineer | Junior Engineer | ORD/000278/2024-2025 | 583/RS | 13/03/2025 | 13/03/2026 | IMAGIN | 334.75 | 0 | 0 | 25
4 | NADIA |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Nadia and Birbhum districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19356 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Nadia District. | Assistant Engineer | Junior Engineer | ORD/000278/2024-2025 | 583/RS | 13/03/2025 | 13/03/2026 | IMAGIN | 334.75 | 0 | 0 | 25
5 | BIRBHUM |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Nadia and Birbhum districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19356 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Birbhum District. | Assistant Engineer | Junior Engineer | ORD/000279/2024-2025 | 582/RS | 13/03/2025 | 13/03/2026 | IMAGIN | 331.95 | 0 | 0 | 25
6 | NADIA |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Nadia and Birbhum districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19356 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Birbhum District. | Assistant Engineer | Junior Engineer | ORD/000279/2024-2025 | 582/RS | 13/03/2025 | 13/03/2026 | IMAGIN | 331.95 | 0 | 0 | 25
Total | [13 empty] | 1544.05 | 0 | 0