## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Birbhum, Purba Barddhaman, North 24 Parganas & South 24 Parganas District of West Bengal. | SM/10541 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Jal Swapna Project in the State of West Bengal For 10(Ten) Zone covering entire District as state below. Purba Bardhaman , Birbhum , Bankura ,Jhargram ,Purulia , Paschim Bardhaman |  | Junior Engineer | ORD/000130/2022-2023 | 3102/RS | 02/06/2022 | 01/06/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 718.05 | 0 | 0 | 46
2 | NORTH 24 PARGANAS |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Birbhum, Purba Barddhaman, North 24 Parganas & South 24 Parganas District of West Bengal. | SM/10541 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Jal Swapna Project in the State of West Bengal For 10(Ten) Zone covering entire District as state below. Purba Bardhaman , Birbhum , Bankura ,Jhargram ,Purulia , Paschim Bardhaman |  | Junior Engineer | ORD/000130/2022-2023 | 3102/RS | 02/06/2022 | 01/06/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 718.05 | 0 | 0 | 46
3 | PURBA BARDHAMAN |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Birbhum, Purba Barddhaman, North 24 Parganas & South 24 Parganas District of West Bengal. | SM/10541 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Jal Swapna Project in the State of West Bengal For 10(Ten) Zone covering entire District as state below. Purba Bardhaman , Birbhum , Bankura ,Jhargram ,Purulia , Paschim Bardhaman |  | Junior Engineer | ORD/000130/2022-2023 | 3102/RS | 02/06/2022 | 01/06/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 718.05 | 0 | 0 | 46
4 | SOUTH 24 PARGANAS |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Birbhum, Purba Barddhaman, North 24 Parganas & South 24 Parganas District of West Bengal. | SM/10541 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Jal Swapna Project in the State of West Bengal For 10(Ten) Zone covering entire District as state below. Purba Bardhaman , Birbhum , Bankura ,Jhargram ,Purulia , Paschim Bardhaman |  | Junior Engineer | ORD/000130/2022-2023 | 3102/RS | 02/06/2022 | 01/06/2025 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 718.05 | 0 | 0 | 46
5 | BIRBHUM |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Birbhum, Purba Barddhaman, North 24 Parganas & South 24 Parganas District of West Bengal. | SM/10541 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Jal Swapna Project in the State of West Bengal For 10(Ten) Zone covering entire District as state below. Murshidabad , Nadia, North 24 Pargana , South 24 Parganas, Howrah, Hooghly |  |  | ORD/000129/2022-2023 | 3101/RS | 02/06/2022 | 01/06/2025 | IRCLASS SYSTEMS AND SOLUTIONS PVT LTD | 718.05 | 0 | 0 | 57
6 | NORTH 24 PARGANAS |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Birbhum, Purba Barddhaman, North 24 Parganas & South 24 Parganas District of West Bengal. | SM/10541 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Jal Swapna Project in the State of West Bengal For 10(Ten) Zone covering entire District as state below. Murshidabad , Nadia, North 24 Pargana , South 24 Parganas, Howrah, Hooghly |  |  | ORD/000129/2022-2023 | 3101/RS | 02/06/2022 | 01/06/2025 | IRCLASS SYSTEMS AND SOLUTIONS PVT LTD | 718.05 | 0 | 0 | 57
7 | PURBA BARDHAMAN |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Birbhum, Purba Barddhaman, North 24 Parganas & South 24 Parganas District of West Bengal. | SM/10541 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Jal Swapna Project in the State of West Bengal For 10(Ten) Zone covering entire District as state below. Murshidabad , Nadia, North 24 Pargana , South 24 Parganas, Howrah, Hooghly |  |  | ORD/000129/2022-2023 | 3101/RS | 02/06/2022 | 01/06/2025 | IRCLASS SYSTEMS AND SOLUTIONS PVT LTD | 718.05 | 0 | 0 | 57
8 | SOUTH 24 PARGANAS |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Birbhum, Purba Barddhaman, North 24 Parganas & South 24 Parganas District of West Bengal. | SM/10541 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Jal Swapna Project in the State of West Bengal For 10(Ten) Zone covering entire District as state below. Murshidabad , Nadia, North 24 Pargana , South 24 Parganas, Howrah, Hooghly |  |  | ORD/000129/2022-2023 | 3101/RS | 02/06/2022 | 01/06/2025 | IRCLASS SYSTEMS AND SOLUTIONS PVT LTD | 718.05 | 0 | 0 | 57
Total | [13 empty] | 5744.4 | 0 | 0