## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | SM/06964 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of CHAKTENTUL Piped Water Supply Scheme at Chaktentul (1 No Part, 2 Nos Habitation), Bharatpur (2 Nos Habitation) Village (Mouza), Galsi-I Block under Burdwan Division, PHE Dte.(Agreement No. 71/2020-2021 OF SE/CC/PHE. DTE.) | AE(HQs) | J.E. 2 BURDWAN | ORD/000128/2020-2021 | 5005/BWD | 10/12/2020 | 10/03/2021 | SUPRIYA RAY | 75.14 | 75.59 | 100.6 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | SM/06964 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Chaktentul village and Chaktentul habitation of Chaktentul piped water supply scheme within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | AE(HQs) | J.E. 2 BURDWAN | ORD/000700/2020-2021 | 4455/BWD | 10/11/2020 | 10/12/2020 | SAIKAT RAY | 4.92 | 9.84 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | SM/06964 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 26/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | SM/06964 | Retrofitting | Repairing of valve chamber & Construction of new valve chamber and supply of sluice valve at Head Works Site for CHAKTATUL PWSS within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000932/2023-2024 | 905/DSD | 15/12/2023 | 14/01/2024 | SAIKAT RAY | 0.97 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | SM/06964 | Retrofitting | Supply of 10 mm NB Gun-metal Ferrul conforming to IS:2692-1989 for water tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division PHE Dte. and delivered at Barsul Divisional Store. [Part-6] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000199/2021-2022 | 3402/BWD | 24/06/2021 | 24/07/2021 | A.K. SIKDAR | 91.8 | 50.49 | 55 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | SM/06964 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-7] | Assistant Engineer |  | ORD/000348/2021-2022 | 2942/BWD | 04/05/2021 | 14/05/2021 | KISHORE GHOSH | 3.94 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | SM/06964 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the month of June & July'23. |  |  | BILL/00792/2023-2024 | 633/JJM | 13/09/2023 | 13/09/2023 | SUJAUDDIN SEKH | 0.78 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | SM/06964 | Retrofitting | Hire & fuel charges of vehicle Car No.-WB-37C-8293 for the month of August'2023. |  |  | BILL/01036/2023-2024 | 746/JJM | 11/10/2023 | 11/10/2023 | SUJAUDDIN SEKH | 0.39 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | SM/06964 | Retrofitting | Vehicle bill for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of May'23. |  |  | BILL/00614/2023-2024 | 562/JJM | 24/08/2023 | 24/08/2023 | SUJAUDDIN SEKH | 0.4 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | SM/06964 | Retrofitting | Laying of interconnection of Head Works Site to distribution main line for CHAKTATUL PWSS within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000933/2023-2024 | 906/DSD | 15/12/2023 | 29/01/2024 | SAIKAT RAY | 0.95 | 0 | 0 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | SM/06964 | Retrofitting | Vehicle bill for the month of November'23. |  |  | BILL/01674/2023-2024 | 1138/JJM | 29/12/2023 | 29/12/2023 | SUJAUDDIN SEKH | 0.38 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | SM/06964 | Retrofitting | Inter Connection From TW_3 to Main Distribution Pipeline (DI/UPVC) and Mechanical joints at 3rd TW site and Sukdal UPVC Pipe laying,Construction of different dia Sluice valve chamber in different sizes,Concrete road renovation and Head Work (TW-1) Site Drain Construction for Chaktentul Water Supply Schemes of GALSI-I Block under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Contractual Junior Engineer_5 | ORD/000115/2025-2026 | 1235/DWSD | 01/08/2025 | 15/09/2025 | SAIKAT RAY | 4.33 | 0 | 0 | 0
Total | [13 empty] | 405 | 135.92 | 33.56