## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bhatkunda Piped Water Supply Scheme | SM/07547 | Retrofitting | Extension of UPVC pipeline of laying distribution system at Moukata village at Bhatkunda and its adjoining mouzas water supply scheme within Ausgram-II Block under Durgapur Sub-Division under Burdwan Division, PHE Dte. [Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000835/2020-2021 | 171/DSD | 19/02/2021 | 12/03/2021 | SHUBHRA KANTI GHOSH | 4.62 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bhatkunda Piped Water Supply Scheme | SM/07547 | Retrofitting | Land development and Construction of culvert and approach road at 2nd tubewell site of Bhatkunda Water Supply Scheme within Durgapur Sub Division Under Burdwan Division, PHE Dte.[SL-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000119/2022-2023 | 337/DSD | 27/06/2022 | 27/07/2022 | RAM MOHAN MUKHERJEE | 3.33 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bhatkunda Piped Water Supply Scheme | SM/07547 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bhatkunda Piped Water Supply Scheme at Bhatkunda (Part) Village (Adibasi Para, Bhatkunda (P), Boldanga Adibashipara habitation), Moukota (Part) Village (Adibashipara, Moukota (P) habitation), Parisha Village, Chaktilong Village, Ranngakhila Village (4Nos. habitations), Balarambati Village & Jijira Village (2 Nos. habitations) Ausgram - II Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000015/2021-2022 | 3205/BWD | 09/06/2021 | 17/02/2023 | ASHOK KUMAR GHOSH | 55.74 | 41.6 | 74.63 | 100
Total | [13 empty] | 63.7 | 41.6 | 65.31