## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme | SM/07548 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Dwariapur Piped Water Supply Scheme at Gonna (1 No. Habitation), Alutia (Part), Dwariapur (7Nos Habitation) & Lakshmiganj (5 Nos Habitation) Village (Mouza), Ausgram-I Block under Burdwan Division, PHE Dte.[Agreement No. 109/2020-2021 OF SE/CC/PHE. DTE.] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000601/2020-2021 | 1600/BWD | 22/02/2021 | 23/04/2021 | RANADHIR SINHA | 81.21 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme | SM/07548 | Retrofitting | Restoration of damaged pipeline of distribution main at Laxmiganj village and laying of parallel line at Gonna village for providing FHTC within Dwariapur W/S Scheme in Ausgram-II Block under Burdwan Division, P.H.E. Dte. [Gr.-G] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000336/2021-2022 | 06/DSD | 03/01/2022 | 02/02/2022 | RANADHIR SINHA | 2.11 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme | SM/07548 | Retrofitting | Restoration of damaged concrete road in connection with laying distribution system at Laxmiganj, Gonna and Gopinathbati village within Dwariapur Piped Water Supply Scheme at Ausgram-I Block within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Gr.-H] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000451/2021-2022 | 80/DSD | 11/02/2022 | 26/02/2022 | RANADHIR SINHA | 4.73 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme | SM/07548 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Ausgram-I Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000366/2021-2022 | 120/BWD | 07/01/2022 | 06/02/2022 | ANIRUDDHA FARUQUE | 12.33 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme | SM/07548 | Retrofitting | Making Connection with Rising Main And Over Head Reservoir of Dwariapur W/S Scheme within Durgapur Sub-Division in Ausgram-I Block under Burdwan Division, P.H.E. Dte.[Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000551/2021-2022 | 133/DSD | 02/03/2022 | 17/03/2022 | RANADHIR SINHA | 0.34 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme | SM/07548 | Retrofitting | Restoration of damaged concrete road in connection with providing FHTC work at Laxmiganj, Gonna and Gopinathbati and Dwariapur village within Dwariapur Piped Water Supply Scheme at Ausgram-I Block within Durgapur Sub-Division under Burdwan Division, PHE Dte.[SL-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000621/2021-2022 | 163/DSD | 16/03/2022 | 31/03/2022 | RANADHIR SINHA | 4.12 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme | SM/07548 | Retrofitting | Modification to the distribution network by making a loop to augment the water supply to FHTC at Gopinathbati village of Dwariyapur and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte._2nd call[SL-05] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000057/2023-2024 | 180/DSD | 18/04/2023 | 09/05/2023 | ANIRUDDHA FARUQUE | 0.92 | 0 | 0 | 100
Total | [13 empty] | 105.77 | 0 | 0