## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block | SM/07781 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Joykrishnapur Piped Water Supply Scheme at Joykrishnapur (4 Nos Habitation), Pilgram & Taranagar (2 Nos Habitation) Village (Mouza), Galsi-II Block under Burdwan Divn., PHE Dte.[Agreement No. 609/BWD OF 2020-2021] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000380/2020-2021 | 752/BWD | 29/01/2021 | 15/03/2021 | SUDHAMAY MAJUMDAR | 43.97 | 73.64 | 167.48 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block | SM/07781 | Retrofitting | Restoration of damaged pipeline of distribution main for construction of drain, concrete road etc. at various point at Jaykrishnapur, Taranagar and Pilgram village for providing FHTC within Jaykrishnapur W/S Scheme in Galsi-II Block under Burdwan Division, P.H.E. Dte.[SL-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000622/2021-2022 | 162/DSD | 16/03/2022 | 15/04/2022 | SUDHAMAY MAJUMDAR | 4.81 | 4.78 | 99.51 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block | SM/07781 | Retrofitting | Sinking of 200mm dia River bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Taranagar village under Joykrishnapur water supply scheme,Block -Galsi-II, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000330/2022-2023 | 533/DSD | 22/08/2022 | 12/09/2022 | ANIRUDDHA FARUQUE | 4.35 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block | SM/07781 | Retrofitting | Sinking of 200mm dia River bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Simuliya village under Joykrishnapur water supply scheme,Block -Galsi-II, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000331/2022-2023 | 534/DSD | 22/08/2022 | 12/09/2022 | SANDIPAN SENGUPTA | 4.35 | 4.36 | 100.12 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block | SM/07781 | Retrofitting | Making Connection with 90 mm dia uPVC pipe within Node 162-168 for improvement of water supply to FHTC at Taranagar village within Jaykrishnapur and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-24] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000866/2022-2023 | 722/DSD | 30/12/2022 | 29/01/2023 | TARAMA AGENCY | 2.07 | 1.98 | 95.62 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block | SM/07781 | Retrofitting | Laying of parallel line with 90 mm dia uPVC pipe within Node 86-88 and providing air valve for improvement of water supply to FHTC at Pilgram village within Jaykrishnapur and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-I) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000464/2021-2022 | 81/DSD | 11/02/2022 | 13/03/2022 | TARAMA AGENCY | 3.12 | 3.02 | 96.64 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block | SM/07781 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of April'23. |  |  | BILL/00293/2023-2024 | 203/JJM | 01/06/2023 | 01/06/2023 | SUJAUDDIN SEKH | 0.4 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block | SM/07781 | Retrofitting | Vehicle bill for the month of September & October'2023. |  |  | BILL/01676/2023-2024 | 961/JJM | 01/12/2023 | 01/12/2023 | SUJAUDDIN SEKH | 0.65 | 0 | 0 | 0
Total | [13 empty] | 63.72 | 87.78 | 137.76