## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block | SM/07807 | Retrofitting | Extension of pipeline including water tap connection (FHTC) at Pubar Vill [Kamalpur & Pubar (Part) Hab.] of PUBAR and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte._2ND CALL. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000175/2021-2022 | 6105/BWD | 08/10/2021 | 07/11/2021 | ANWESHA CONSTRUCTION | 29.76 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block | SM/07807 | Retrofitting | Extension of pipeline including water tap connection (FHTC) at Pubar Vill [Kamalpur & Pubar (Part) Hab.] of PUBAR and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte._2ND CALL | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000193/2021-2022 | 6104/BWD | 08/10/2021 | 07/11/2021 | ANWESHA CONSTRUCTION | 29.76 | 29.22 | 98.18 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block | SM/07807 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Ausgram-II Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000472/2021-2022 | 940/BWD | 17/02/2022 | 19/03/2022 | NANDY UDYOG | 11.82 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block | SM/07807 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Pubar (Part) village (Pubar (Part) habitation) of Pubar Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [Sl. No. : ¿16¿] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000420/2020-2021 | 66/BWD | 05/01/2021 | 20/01/2021 | SUBRATA GUPTA | 4.86 | 4.86 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block | SM/07807 | Retrofitting | Extension of Pipeline with Providing Functional Household Tap Connection (FHTC) within the command area of PUBER Piped Water Supply Scheme , Block- Ausgram-II within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000457/2021-2022 | 77/DSD | 11/02/2022 | 13/03/2022 | ANWESHA CONSTRUCTION | 4.75 | 2.94 | 61.76 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block | SM/07807 | Retrofitting | Relaying of pipeline damaged by construction of Road/Drain etc. at different location of Pubar and its adjoining mouzas water supply scheme at Ausgram-II Block within Durgapur Sub-Division, under Burdwan Division, PHE Dte. [SL-20] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000862/2022-2023 | 719/DSD | 30/12/2022 | 29/01/2023 | ASRUL HAQUE MONDAL | 0.88 | 0.88 | 99.33 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block | SM/07807 | Retrofitting | Laying parallel pipeline to increase the water supply towards Kaldanda of PUBER and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000132/2022-2023 | 344/DSD | 30/06/2022 | 30/07/2022 | ANWESHA CONSTRUCTION | 4.81 | 4.81 | 99.98 | 1
Total | [13 empty] | 86.66 | 42.7 | 49.28